## COVER PAGE
ELIAS MOTSOALEDI LOCAL MUNICIPALITY
2021 / 2022 First quarter performance report
A RE BELEGANENG

## summary 01
1st QUARTER PERFORMANCE REPORT
1. Introduction
The Service Delivery and Budget Implementation Plan provides the basis for measuring performance in service delivery against the end of the year targets and implementing the budget. In addition, the SDBIP creates a line of accountability from senior management to all employees. The SDBIP convert the needs of communities into measurable performance measures, indicators and targets.
The SDBIP explicitly defines lines of accountability and responsibility. The Municipal Performance targets are monitored on quarterly basis and as envisaged in the SDBIP are then cascaded to individual managers and will form the basis of the quarterly performance coaching sessions.
2. Executive Summary
The table below represents the institutional performance for the 1st Quarter per department:
Key Performance Area | departments | 1st quarter target | Achieved KPIs | Not achieved KPIs | not applicable | Total Percentage achieved %
1 | Development planning | 8 | 8 | 0 |  | 100%
2 | Executive support | 8 | 7 | 1 |  | 88%
3 | Corporate services | 8 | 8 | 0 |  | 100%
7 | Municipal Managers' office | 14 | 12 | 2 |  | 86%
5 | Finance | 6 | 5 | 1 |  | 83%
6 | Community services | 16 | 10 | 1 | 5 | 91%
7 | Infrastructure | 24 | 15 | 8 | 1 | 65%
| TOTAL | 84 | 65 | 13 | 6 | 83%
The table below represents the institutional performance for the 1st Quarter per Key Performance Area:
Key Performance Area Number | Key Performance Area | Total 1st quarter target | Achieved KPIs | Not achieved KPIs | not applicable | Total Percentage achieved %
1 | Spatial Rationale | 4 | 4 | 0 |  | 100%
2 | Institutional Development & Transformation | 8 | 7 | 1 |  | 88%
3 | Local Economic Development | 2 | 1 | 1 |  | 50%
4 | Basic Service Delivery | 30 | 21 | 3 | 6 | 88%
5 | Financial Management & Viability | 7 | 6 | 1 |  | 86%
6 | Good Governance & Public Participation | 15 | 13 | 2 |  | 80%
| Total | 66 | 52 | 8 | 6 | 88%

## Planning
DEVELOPMENT PLANNING
KPA 1: SPATIAL DEVELOPMENT ANALYSIS AND RATIONALE
Strategic objectives: To promote intergrated human settlements
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience
Land Use Management | % of land use applications received and processed within 90 days | n/a |  | 100% | 100% of land use applications received and processed within 90 days by 30 September 2021 | 100% of land use applications received and processed within 90 days by 30 September 2021 | None | none | land use application register | achieved
| % of new building plans of less than 500 square metres assessed within 10 days of receipt of plans | n/a |  | 100% | 100% of new buildings plans of less than 500 sqm assessed within 10 days upon receipt of plans by 30 September 2021 | 100% of new buildings plans of less than 500 sqm assessed within 10 days upon receipt of plans by 30 September 2021 | None | none | building plans application register | achieved
| % of new building plans of more than 500 square meters assessed within 28 days of receipt of plans | n/a |  | 100% | 100% of new building plans of more than 500 square meters assessed within 28 days of receipt of plans by 30 September 2021 | 100% of new building plans of more than 500 square meters assessed within 28 days of receipt of plans by 30 September 2021 | None | none | building plans application register | achieved
Compliance with National Building Regulations | % of inspections conducted on building construction with an approved plan to ensure compliance with Sec.6©and 17 (b) of National Building Regulations and Building Standards Act | n/a |  | 100% | 100% of inspections conducted on building construction with an approved plan to ensure compliance with Sec.6©and 17 (b) of National Building Regulations and Building Standards Act by 30 September 2021 | 100% of inspections conducted on building construction with an approved plan to ensure compliance with Sec.6©and 17 (b) of National Building Regulations and Building Standards Act by 30 September 2021 | None | none | inspection report | achieved
KPA 3: LOCAL ECONOMIC DEVELOPMENT
Strategic objectives: To promote conducive enviroment for economic growth and development
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience
EPWP | Number of job opportunities provided through EPWP grant (GKPI) | EPWP grant |  | 69 | n/a | n/a | n/a | n/a | n/a | n/a
| Number of SMME’s and Co-operatives capacity building workshops/ training held(LED training) | Opex |  | 12 | 3 SMME’s and Co-operatives capacity building workshops/ training held by 30 June 2022 (LED training) | 6 SMME’s and Co-operatives capacity building workshops/ training held by 30 June 2022 (LED training) | none | none | reports and attendance registers | achieved
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic objectives : To enhance good governance and public participation
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr | Progress to date | Challenges | Reason for Varience
Audit | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year | n/a |  | Qualified audit opinion | n/a | n/a | n/a | n/a | n/a | n/a
| % Internal Audit Findings resolved per quarter as per the Audit Plan | n/a |  | 92% | 100% Internal Audit Findings resolved per quarter as per the Audit Plan by 30 September 2021 | 100% Internal Audit Findings resolved per quarter as per the Audit Plan by 30 September 2021 | none | none | Quarterly IA follow up report | achieved
Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter | n/a |  | 100% | 25% execution of identified risk management plan within prescribed timeframes per quarter by 30 September 2021 | 33% execution of identified risk management plan within prescribed timeframes per quarter by 30 September 2021 | none | none | Quartely Risk assessent reports | achieved
KPA 5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Objectives : To improve sound and municipal financial management
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience
SCM | Number of SCM deviation reports submitted to municipa manager (reduction of number of deviations) | n/a |  | 9 | Maximum of 1 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 30 September 2021 | 0 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 30 September 2021 | none | none | Signed deviation report | achieved

## Corporate Services
CORPORATE SERVICES
KPA 2: INSTITUTIONAL DEVELOPMENT AND MUNICIPAL TRANSFORMATION
Strategic Objectives: To build capabe, responsive, accountable, effective and efficient municipal institutions and administration
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience
employment equity | review of the Employment Equity Plan | n/a |  | new | n/a | n/a | n/a | n/a | n/a | n/a
| Submission of employment equity report to DOL by 31st January 2022 | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
| % of employees with disabilities | n/a |  | new | n/a | n/a | n/a | n/a | n/a | n/a
Skills programme | Number of employees approved for study financial assistance | Opex |  | 0 | n/a | n/a | n/a | n/a | n/a | n/a
WSP | Approval of reviewed WSP (work skills plan) | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
| % of a municipality's payroll budget on training and education of employees | 1% |  | 80% | n/a | n/a | n/a | n/a | n/a | n/a
LLF | Number of LLF meetings held | n/a |  | 9 | 2 LLF meetings held by 30 September 2021 | 2 LLF meetings held: *03/08/2021 *03/09/2021 | none | none | attendance register and minutes | achieved
ICT | % of reportet ICT incidents resolved | n/a |  | new | 90% - 100% % of reported ICT incidents resolved by 30 September 2021 | 100% (89/89) of reported ICT incidents resolved by 30 September 2021 | None | None | ICT Job Card | achieved
| turnaround time in placing documents and information on the municipal webite | 187020 |  | new | Placement of documents and information on municipal website 5 (five)working days from the date submitted to ICT by 30 September 2021 | Documents and information placed on municipal website within 5 (five)working days from the date submitted to ICT by 30 September 2021 | None | None | *Website Register * SITA email confirming placement of documents and information | achieved
| Number of ICT Service Providers Peformance Monitoring and Evaluation meetings held | n/a |  | 4 | 1 ICT Service Providers Peformance Monitoring and Evaluation meetings held by 30 September 2021 | 1 ICT Service Providers Peformance Monitoring and Evaluation meetings held by 23 September 2021 | None | None | Attendance Register and Minutes | achieved
Occupational health and safety (OHS) | % expenditure of uniform and protective clothing | 1000000 |  | new | n/a | n/a | n/a | n/a | n/a | n/a
Occupational health and safety (OHS) | Medical Surveillance conducted | 244165 |  | new | n/a | n/a | n/a | n/a | n/a | n/a
Occupational health and safety (OHS) | First Aid in the Workplace/ Risk Based Primary Emergency Care Training for Health and Safety Committee held | n/a |  | new | n/a | n/a | n/a | n/a | n/a | n/a
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic objectives : To enhance good governance and public participation
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr | Progress to date | Challenges | Reason for Varience
Audit | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year | n/a |  | Qualified audit opinion | n/a | n/a | n/a | n/a | n/a | n/a
| % Auditor General matters resolved as per the approved audit action plan | n/a |  | 87% | n/a | n/a | n/a | n/a | n/a | n/a
| % Internal Audit Findings resolved per quarter as per the Audit Plan | n/a |  | 92% | 100% Internal Audit Findings resolved per quarter as per the Audit Plan by 30 September 2021 | 100% Internal Audit Findings resolved per quarter as per the Audit Plan by 30 September 2021 | None | None | Quarterly IA follow up report | achieved
Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter | n/a |  | 100% | 25% execution of identified risk management plan within prescribed timeframes per quarter by 30 September 2021 | 27% (4/15) execution of identified risk management plan within prescribed timeframes per quarter by 30 September 2021 | None | None | Quartely Risk assessent reports | achieved
CAPITAL PROJECTS
ward no | Project | key performance indicator | Original Budget R 000's 2021/22 | Expenditure | Audited Baseline 2019/20 | 1st Qtr Target | Progress to date | Challenges | Reason for Varience | Evidence | Achieved / Not Achieved
n/a | Computer Equipment | % expenditure on computer equipment | 460000 |  | 100% | 10% minimum expenditure on computer equipment by 30 September 2021 | 99,8% (R459,400 / R460,000) expenditure on computer equipment by 30 September 2021 | Additional computer equipments for newly appointed interns | Consider upward budget adjustment | Expenditure report / screen shot | achieved
KPA 5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Objectives : To improve sound and municipal financial management
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience
SCM | Number of SCM deviation reports submitted to municipa manager (reduction of number of deviations) | n/a |  | 9 | Maximum of 1 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 30 September 2021 | 0 SCM deviation reports submitted to municipal manager (there was no deviation) by 30 September 2021 | None | None | Signed deviation report | achieved

## Office of MM
MUNICIPAL MANAGER'S OFFICE
KPA 2 : INSTITUTIONAL DEVELOPMENT AND MUNICIPAL TRANSFORMATION
Strategic Objectives : To build capable, responsive, accountable, effective and efficient municipal institutions and administration
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/2022 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience
Performance Management | % of KPIs and projects attainin organisational targets (total organisation) | n/a |  | 49% | 25% of KPIs and projects attainin organisational targets (total organisation) by 30 September 2021 | 88% of KPIs and projects attainin organisational targets (total organisation) by 30 September 2021 | none | none | performance report | achieved
| Final SDBIP approved by Mayor within 28 days after approval of IDP/ Budget | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
| number of litigations reports created | n/a |  | new | 1 litigations report created by 30 June 2022 | 1 litigations report created by 30 June 2022 | none | none | litigation reports | achieved
KPA 5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Objectives : To improve sound and municipal financial management
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience
Expenditure | % spend of the Total Operational Budget excluding non-cash items | Opex |  | 95% | 25% spend of the Total Operational Budget excluding non-cash items by the 30 September 2021 | 26% spend of the Total Operational Budget excluding non-cash items by the 30 September 2021 | none | none | Budget report | achieved
Expenditure | Remuneration (Employee Related Costs and Councillors Remuneration) as % of Total Operating Expenditure per quarter | Opex |  | 34% | 25% to 40% Remuneration (Employee Related Costs and Councillors Remuneration) as % of Total Operating Expenditure per quarter by 30 September 2021 | 38% Remuneration (Employee Related Costs and Councillors Remuneration) as % of Total Operating Expenditure per quarter by 30 September 2021 | none | none | Section 71 report | achieved
SCM | Number of SCM deviation reports submitted to municipa manager (reduction of number of deviations) | n/a |  | 9 | Maximum of 1 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 30 September 2021 | 0 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 30 September 2021 | none | none | Signed deviation report | achieved
KPA 6 : GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic Objectives : To enhance good governance and public participation
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience
Good Governance and oversight | Submission of Final audited (2020-2021) consolidated Annual Report to Council by 31 January 2022 | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
| submisson of annual report oversight report to council by March 2022 | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
| 2021 /2022 IDP review process plan approved by August 2021 |  |  | 1 | 1 2021 /2022 IDP review process plan approved by August 2021 | 1 2021 /2022 IDP review process plan approved by August 2021 | none | none | council resolution | achieved
IDP Development | Final IDP tabled and approved by Council by the 31 May 2022 | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
Audit | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year | n/a |  | Qualified audit opinion | n/a | n/a | n/a | n/a | n/a | n/a
| % of Auditor General matters resolved as per the approved audit action plan (Total organisation) | n/a |  | 87% | n/a | n/a | n/a | n/a | n/a | n/a
Audit | % Internal Audit Findings resolved per quarter as per the Audit Plan (total organisation) | n/a |  | 92% | 100% Internal Audit Findings resolved per quarter as per the Audit Plan (total organisation) by 30 September 2021 | 65% Internal Audit Findings resolved per quarter as per the Audit Plan (total organisation) by 30 September 2021 | None | Implementtion of action plans in progress | Quarterly IA follow up report | Not Achieved
Risk Management | Number of risk based internal audits conducted | n/a |  | new | 1 risk based internal audits conducted by 30 September 2021 | 0 risk based internal audits conducted by 30 September 2021 | none | none | Risk based audit reports | not achieved
Risk Management | Number of security risk asessment conducted | n/a |  | 4 | 1 security risk asessment conducted by 30 September 2021 | 1 security risk asessment conducted by 30 September 2021 | none | none | Quartely Risk Assessment report | achieved
| number of project risk assessments conducted | n/a |  | 2 | 1 project risk assessments conducted by 30 September 2021 | 1 project risk assessments conducted by 30 September 2021 | none | none | Quartely Risk assessment report | achieved
| Number of strategic and operational risk assessment conducted | n/a |  | new | 1 strategic and operational risk assessment conducted by 30 September 2021 | 1 strategic and operational risk assessment conducted by 30 September 2021 | none | none | Assessment report | achieved
| Number of risk management training conducted | n/a |  | new | n/a | n/a | n/a | n/a | n/a | n/a
| Number of Risk Management reports submitted to the Risk Management Committee per quarter | n/a |  | 4 | 1 Risk Management reports submitted to the Risk Management Committee per quarter by 30 September 2021 | 1 Risk Management reports submitted to the Risk Management Committee per quarter by 30 September 2021 | none | none | Quartely Risk assessment report | achieved
| Number of quartely Risk Management Committtee meetings convened | n/a |  | 4 | 1 quartely Risk Management Committtee meetings convened by September 2021 | 1 quartely Risk Management Committtee meetings convened by September 2021 | none | none | attendance reigister and minutes | achieved
Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter (Total organisation) | n/a |  | 100% | 25% execution of identified risk management plan within prescribed timeframes per quarter (Total organisation) by 30 September 2021 | 31% execution of identified risk management plan within prescribed timeframes per quarter (Total organisation) by 30 September 2021 | none | none | Quartely Risk assessment reports | achieved

## Infrastructure
INFRASTRUCTURE
KPA 3: LOCAL ECONOMIC DEVELOPMENT
Strategic Objectives: To promote conducive enviroment for economic growthe and development
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience |  | Achieved / Not Achieved
EPWP | number of job opportunities created through infrastructure projects (GKPI) | MIG/INEP/EMLM |  | 253 | 90 job opportunities created through infrastructure projects by 30 September 2021 (GKPI) | 52 job opportunities created through infrastructure projects by 30 September 2021 (GKPI) | Only three projects are at implementation stage . 6 projects are at procurement stage and 1 project is still on hold to change of design | to continue with appointment as soon as the remaining projects are at implementation stage | List of appointees | not achieved
KPA 4: BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Strategic Objectives: To provide for basic services delivery and sustainable infrastractural development
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience | Evidence | Achieved / Not Achieved
Roads and storm water | kilometers of graveled roads re-gravelled | n/a |  | 120.5km | 20km of gravel municipal roads/streets re-regravelled by 30 September 2021 | 22km of gravel municipal roads/streets re-regravelled by 30 September 2021 | None | None | completion certificates | achieved
KPA 5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Objectives : To improve sound and sustainable municipal financial management
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience |  | Achieved / Not Achieved
Project Management | % spending on MIG funding by the 30 June 2022 | MIG |  | 91% | 10% spending on MIG funding by the 30 September 2021 | 33.41% spending on MIG funding by the 30 September 2021 | None | None | MIG monthly report | achieved
Electricity | % spending on INEP funding by 30 June 2022 | INEP |  | 100% | 25% spending on INEP funding by 30 September 2021 | 4% spending on INEP funding by 30 September 2021 | Panel of contractors are apppointed awaiting for allocation of projects | effective spending of the INEP grant as soon as projects are allocated and implemented | INEP monthly report | not achieved
SCM | Number of SCM deviation reports submitted to municipa manager (reduction of number of deviations) | n/a |  | 9 | Maximum of 1 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 30 September 2021 | 0 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 30 September 2021 | None | None | Signed deviation report | achieved
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic objectives : To enhance good governance and public participation
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr | Progress to date | Challenges | Reason for Varience
Audit | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year | n/a |  | Qualified audit opinion | n/a | n/a | n/a | n/a | n/a | n/a
| % Auditor General matters resolved as per the approved audit action plan | n/a |  | 87% | n/a | n/a | n/a | n/a | n/a | n/a
| % Internal Audit Findings resolved per quarter as per the Audit Plan | n/a |  | 92% | 100% Internal Audit Findings resolved per quarter as per the Audit Plan by 30 September 2021 | 62% Internal Audit Findings resolved per quarter as per the Audit Plan by 30 September 2021 | Contract of the service provider has expired | Tender advert issued for appointment of new service provider to implement the project to install the Anti-Siphoning to address the finding. | Quarterly IA follow up report | not achieved
Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter | n/a |  | 100% | 25% execution of identified risk management plan within prescribed timeframes per quarter by 30 September 2021 | 30% execution of identified risk management plan within prescribed timeframes per quarter by 30 September 2021 | None | none | Quartely Risk assessent reports | achieved
KPA 2: INSTITUTIONAL DEVELOPMENT AND MUNICIPAL TRANSFORMATION
Strategic Objectives: To build capable, responsive, accountable, effective and efficient municipal institutions and administration
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience |  | Achieved / Not Achieved
municipal infrastructure grants (MIG) | number of MIG reports submitted to CoGHSTA | n/a |  | 12 | 3 MIG reports submitted to CoGHSTA by 30 September 2021 | 3 MIG reports submitted to CoGHSTA by 30 September 2021 | None | None | proof of submission | achieved
department of energy ( DOE) | number of INEP reports submitted to department of energy | n/a |  | 12 | 3 INEP reports submitted to department of energy by 30 September 2021 | 2 INEP reports submitted to department of energy by 30 September 2021 | Unable to retrieve proof of submission for the month of July | Unable to retrieve proof of submission for the month of July | proof of submission | not achieved

## Infra projects
CAPITAL PROJECTS
KPA 4: BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Strategic objective: To provide for basic services delivery and sustainable infrastructural development
Ward No. | Project | key performance indicator | Original Budget R 000's 2021/22 | Expenditure | Audited Baseline 2019/20 | 1st Qtr Target | Progress to date | Challenges | Reason for Varience | Evidence | Achieved / Not Achieved
n/a | Air conditioners | % processing of procurement request submitted | 300000 | 0 | 50% | 100% processing of procurement request submitted by 30 September 2021 | 0% processing of procurement request submitted by 30 September 2021 | Project is currently on advert stage | procurement will be done soon after appointment of service provider | processed requisition | not achieved
13 | Groblersdal landfill site | upgrading of groblersdal landfill site | 9050000 | 0 | new | advertising of the project by 30 September 2021 | Project is still on hold due to change of Designs as per LEDET request | Project is still on hold due to change of Designs as per LEDET request | Project is still on hold due to chage of Designs as per LEDET request | tender advert | not achieved
13 | Fencing of Game Farm | Fencing of Game Farm | 1100000 | 0 | new | development of specification by 30 September 2021 | no development of specification was done by 30 September 2021 | progress - project is onhold. Budget is frozen | to zero weight the project during budget adjustment | specification | not achieved
13 | upgrading of Groblersdal traffic lights | number of traffic lights intersections upgraded in Groblersdal | 340000 | 0 | new | n/a | n/a | n/a | n/a | n/a | n/a
n/a | Supply and delivery of municipal vehicles | number of vehicles to be procured from the existing lease to buy contract | 800000 | 0 | new | n/a | n/a | n/a | n/a | n/a | n/a
24 | Reticulation of stands with electrical infrastructure at Ga Posa | number of stands reticulated with electrical infrastructure at Ga Posa | 2088000 | 289664 | 5% | appointment of the contractor, site handover and site establishment by 30 September 2021 | appointment of the contractor, site handover and site establishment by 30 September 2021 | none | none | appointment letter | achieved
12 | Reticulation of stands with electrical infrastructure at Maleoskop | designs of stands to be reticulated with electrical infrastructure | 3348000 | 0 | new | appointment of the contractor, site handover and site establishment by 30 September 2021 | appointment of the contractor, site handover and site establishment by 30 September 2021 | none | none | appointment letter | achieved
14 | Reticulation of stands with electrical infrastructure at Masakaneng | number of stands reticulated with electrical infrastructure at masakaneng | 5508000 | 0 | new | appointment of the contractor, site handover and site establishment by 30 September 2021 | appointment of the contractor, site handover and site establishment by 30 September 2021 | none | none | appointment letter | achieved
14 | Reticulation of stands with electrical infrastructure at Matlala Lehwelere | number of stands reticulated with electrical infrastructure at Matlala Lehwelere | 3438000 | 358668 | new | appointment of the contractor, site handover and site establishment by 30 September 2021 | appointment of the contractor, site handover and site establishment by 30 September 2021 | none | none | appointment letter | achieved
19 | Reticulation of stands with electrical infrastructure at Rondebosch | number of stands reticulated with electrical infrastructure at Rondebosch | 1206000 | 0 | new | appointment of the contractor, site handover and site establishment by 30 September 2021 | appointment of the contractor, site handover and site establishment by 30 September 2021 | none | none | appointment letter | achieved
23 | Reticulation of stands with electrical infrastructure at Vlakfontein | number of stands reticulated with electrical infrastructure at Vlakfontein | 5760000 | 118680.73 | new | appointment of the contractor, site handover and site establishment by 30 September 2021 | appointment of the contractor, site handover and site establishment by 30 September 2021 | none | none | appointment letter | achieved
28 | Dipakapakeng access road | upgrading of 2.2km of Dipakapakeng road | 21750000 | 4727298.13 | new | 0km appointment of the contractor, site handover and site establishment by 30 September 2021 | 0km appointment of the contractor, site handover and site establishment by 30 September 2021 | None | None | appointment letter | achieved
27 | upgrading of Tafelkop stadium access road | ugrading of Tafelkop Stadium access road | 13184000 | 5888989.6 | new | advertising of the project by 30 September 2021 | service provider appointed | None | None | appointment letter | achieved
11 | Bloompoort to Uitspanning access road | upgrading of Bloompoort to Uitspanning access road | 13000000 | 8757232.22 | new | advertising of the project by 30 September 2021 | service provider appointed | None | None | appointment letter | achieved
31 | Motetema internal streets | construction of Motetema internal access streets | 1500000 | 0 | 11% | n/a | n/a | n/a | n/a | n/a | n/a
all wards | Rehabilitation of roads/ streets in various wards | Rehabilitation of roads/ streets in various wards | 2500000 | 2875000 | new | 1.4km of roads/ streets in various wards rehabilitated by 30 Septembr 2021 | 1.6km of roads/ streets in waalkral were maintained/rehabilitated by 30 Septembr 2021 | None | None | completion certificate | achieved
21 | upgrading of Kgaphamadi bus road stormwater control | designs of 5200m of Kgaphamadi bus road stormwater control | 1000000 | 65248684.51 | new | 20% scoping report completed by 30 September 2021 | 0% scoping report completed by 30 September 2021 | Still waiting for stormwater detailed design | scoping report will be prepared based on stormwater detailed design | Scoping report | not achieved
n/a | Culverts, road signs, stormwater channels | % expenditure on procurement of culverts road signs for stormwater channels | 500000 | 0 | new | 50% expenditure on procurement of culverts road sig for stormwater channels by 30 September 2021 | 0% expenditure on procurement of culverts road signs for stormwater channels by 30 September 2021 | progress - project is onhold. Budget is frozen | to zero weight the project during budget adjustment | expenditure report | not applicable
|  |  | 86372000 | 88264217.19

## Community Services
COMMUNITY SERVICES
KPA 4: BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Strategic Objectives: To provide for basic services delivery and sustainable infrastructural development
| Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[6 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience
| Waste management | number of reports for waste collection | n/a |  | 8% | 4 reports for waste collection by 30 September 2021 | 5 reports for waste collection by 30 September 2021 | None | None | waste collection reports | Achieved
|  | number of waste received (tons) at landfill site | n/a |  | new | 100 tons of waste received at landfill site by 30 September 2021 | 177.7 tons of waste received at landfill site by 30 September 2021 | None | None | reports on tons received | Achieved
| Education/ Libraries | Number of initiatives held to promote library facilities | n/a |  | 3 | 1 initiatives held to promote library facilities by 30 September 2021 | 1 initiatives held to promote library facilities by 30 September 2021 | None | None | attendance register and reports | Achieved
| Environmental management | number of enviromental awareness conducted | Opex |  | 3 | 1 enviromental awareness conducted by 30 September 2021 | 10 enviromental awareness conducted by 30 September 2021 | None | None | attendance register and reports | Achieved
| Disaster management | Number of disaster awareness campaigns conducted | Opex |  | 3 | 1 disaster awareness campaigns conducted by 30 September 2021 | 1 disaster awareness campaigns conducted by 30 September 2021 | None | None | attendance register and reports | Achieved
|  | % of disaster relief provided | Opex |  | new | 100% of disaster relief cases attended by 30 September 2021 | 100% of disaster relief cases attended by 30 September 2021 | None | None | completed assessment form | Achieved
|  | % of disaster cases reported and attended to within 48 hours | n/a |  | new | 100% of disaster cases reported and attended to within 48 hours by 30 September 2021 | 100% of disaster cases reported and attended to within 48 hours by 30 September 2021 | None | None | completed assessment form | Achieved
| safety and security | number of community safety forum meetings held | n/a |  | 3 | 1 community safety forum meetings held by 30 September 2021 | 2 community safety forum meetings held by 30 September 2021 | None | None | reports and attendance register | Achieved
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic objectives : To enhance good governance and public participation
| Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[6 empty] | 1st Qtr | Progress to date | Challenges | Reason for Varience
| Audit | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year | n/a |  | Qualified audit opinion | n/a | n/a | n/a | n/a | n/a | n/a
|  | % Internal Audit Findings resolved per quarter as per the Audit Plan | n/a |  | 92% | 100% Internal Audit Findings resolved per quarter as per the Audit Plan by 30 September 2021 | 82% Internal Audit Findings resolved per quarter as per the Audit Plan by 30 September 2021 | None | Implementtion of action plans in progress | Quarterly IA follow up report | Not Achieved
| Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter | n/a |  | 100% | 25% execution of identified risk management plan within prescribed timeframes per quarter by 30 September 2021 | 25% execution of identified risk management plan within prescribed timeframes per quarter by 30 September 2021 | None | None | Quartely Risk assessent reports | Achieved
CAPITAL PROJECTS
ward no | Project | key performance indicator | Original Budget R 000's 2021/22 | Expenditure | Audited Baseline 2019/20 | 1st Qtr Target | Progress to date | Challenges | Reason for Varience | Evidence | Achieved / Not Achieved
n/a | Disaster management centre emergency relief store room | Construction of Disaster management centre emergency relief store room | 100000 |  | new | development of specification by 30 September 2021 | no specifications were developed by 30 September 2021 | project is onhold. Budget is frozen | to zero weight the project during budget adjustment | specification | not applicable
13 | upgrading and development of parks | number of parks to be developed and upgraded | 200000 |  | new | development of specification by 30 September 2021 | no specifications were developed by 30 September 2021 | project is onhold. Budget is frozen | to zero weight the project during budget adjustment | specification | not applicable
13 | fencing of Elandsdoorn / Ntwane cemetery | fencing of Elandsdoorn / Ntwane cemetery | 500000 |  | 50% | development of terms of reference (TOR) by 30 September 2021 | No TOR were developed by 30 September 2021 | project is onhold. Budget is frozen | to zero weight the project during budget adjustment | Terms of reference | not applicable
n/a | No illegal dumping boards | procurement of No illegal dumping boards | 200000 |  | new | development of specification by 30 September 2021 | no specifications were developed by 30 September 2021 | project is onhold. Budget is frozen | to zero weight the project during budget adjustment | specification | not applicable
30 | Roosenekaal concrete palisade | upgrading of Roosenekaal concrete palisade | 100000 |  | new | development of specification by 30 September 2021 | no specifications were developed by 30 September 2021 | project is onhold. Budget is frozen | to zero weight the project during budget adjustment | specification | not applicable
KPA 5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Objectives : To improve sound and municipal financial management
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience
SCM | Number of SCM deviation reports submitted to municipa manager (reduction of number of deviations) | n/a |  | 9 | Maximum of 1 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 30 September 2021 | 0 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 30 September 2021 | none | none | Signed deviation report | achieved

## Budget & Treasury
BUDGET AND TREASURY
KPA 4: BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Strategic Objectives: To provide basic services delivery and sustainable infrastructural development
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience
Indigents | number of households in municipal area registered as indigents | 207800 |  | 23% | 1176 households in municipal area registered as indigents by 30 September 2021 | 6942 households in municipal area registered as indigents by 30 September 2021 | n/a | n/a | indigent register | achieved
KPA 5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Objectives : To improve sound and sustainable municipal financial management
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience
Financial management | Cost coverage ratio (GKPI) | n/a |  | 0 | n/a | n/a | n/a | n/a | n/a | n/a
Revenue | % outstanding service debtors to revenue (GKPI) | n/a |  | 26% | n/a | n/a | n/a | n/a | n/a | n/a
Budget | Submission of MTRE Budget to Council 30 days before the start of the new financial year | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
Revenue | % of billed revenue collected | n/a |  | new | 20% of billed revenue collected by 30 September 2021 | 85% of billed revenue collected by 30 September 2021 | none | none | revenue report | achieved
AFS | Audited Annual Financial Statements (AFS) and Audit report submitted to council by 31 January 2022 | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
SCM | number of SCM deviation reports submitted to municipal manager (reduction of number of deviations ) | n/a |  | 9 | Maximum of 1 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 30 September 2021 | 0 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 30 September 2021 | none | none | Signed deviation report | achieved
Expenditure | % Payment of creditors within 30 days | n/a |  | 100% | 100% Payment of creditors within 30 days by 30 September 2021 | 100% Payment of creditors within 30 days by 30 September 2021 | none | none | creditors age analysis | achieved
Assets management | Number of assets verifications conducted | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic objectives : To enhance good governance and public participation
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr | Progress to date | Challenges | Reason for Varience
Audit | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year | n/a |  | Qualified audit opinion | n/a | n/a | n/a | n/a | n/a | n/a
| % Auditor General matters resolved as per the approved audit action plan |  |  | 87% | n/a | n/a | n/a | n/a | n/a | n/a
| % Internal Audit Findings resolved per quarter as per the Audit Plan | n/a |  | 92% | 100% Internal Audit Findings resolved per quarter as per the Audit Plan by 30 September 2021 | 65% Internal Audit Findings resolved per quarter as per the Audit Plan by 30 September 2021 | SOPs not yet developed for BTO divisions, salary disparities, and lack of access for approval of additions and changes on salaries and benefits | The department is still in a process of addressing all Internal Audit findings that are still pending and action plan has been developed in this regard | Quarterly IA follow up report | not achieved
Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter | n/a |  | 100% | 25% execution of identified risk management plan within prescribed timeframes per quarter by 30 September 2021 | 27% execution of identified risk management plan within prescribed timeframes per quarter by 30 September 2021 | none | none | Quartely Risk assessent reports | achieved
CAPITAL PROJECTS
ward no | Project | key performance indicator | Original Budget R 000's 2021/22 | Expenditure | Audited Baseline 2019/20 | 1st Qtr Target | Progress to date | Challenges | Reason for Varience | Evidence | Achieved / Not Achieved
n/a | forklift | % procurement of forklift | 100000 |  | new | n/a | n/a | n/a | n/a | n/a | n/a

## Executive support
EXECUTIVE SUPPORT
KPA 4: BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Strategic Objectives: To provide basic services delivery and sustainable infrastructural development
Programme | Key performance indicator | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience
Transversal programmes | number of Transversal programmes implemented in terms of mainstreaming with respect to HIV/AIDS, Gender, Disabled, Woman and Children Rights, eldery and moral re-generation | Opex |  | 4 | n/a | n/a | n/a | n/a | n/a | n/a
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic objectives : To enhance good governance and public participation
Programme | Key performance indicator | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience
MPAC | number of MPAC quartely reports submitted to council | n/a |  | 3 | 1 MPAC quartely reports submitted to council by 30 September 2021 | 1 MPAC quartely reports submitted to council by 30 September 2021 | none | none | council resolution | achieved
| number of MPAC outreaches initiated | 1000000 |  | 3 | n/a | n/a | n/a | n/a | n/a | n/a
Mayoral campaigns (event promotions) | number of Mayoral outreach projects initiated | 623400 |  | 2 | n/a | n/a | n/a | n/a | n/a | n/a
Speakers programme (event promotions) | number of Speaker's outreach projects initiated | 207800 |  | 2 | n/a | n/a | n/a | n/a | n/a | n/a
Ward committee | number of ward committeee reports submitted to council quartely | n/a |  | 2 | n/a | n/a | n/a | n/a | n/a | n/a
youth programmes | number of youth programmes initiated | Opex |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
communications | number of municipal newsletter printed/ produced | opex |  | 10000 | 1250 municipal newsletter printed/ produced by 30 September 2021 | 2000 municipal newsletter printed/ produced by 30 September 2021 | none | none | delivery note and copy of the newsletter | achieved
| reviewal of communication strategy | n/a |  | 0% | n/a | n/a | n/a | n/a | n/a | n/a
customer services | % of community complaints received and processed | n/a |  | 100% | 100% of community complaints received and processed by 30 September 2021 | 100% of community complaints received and processed by 30 September 2021 | none | none | community complaints register | achieved
customer care | number of customer care implementaion plan and monitoring conducted | n/a |  | new | 1 customer care implementaion plan and monitoring conducted by 30 September 2021 | 1 customer care implementaion plan and monitoring conducted by 30 September 2021 | none | none | implementation and monitoring register | achieved
council resolutions | % council resolutions implemented | n/a |  | new | 25% council resolutions implemented by 30 September 2021 | 25% council resolutions implemented by 30 September 2021 | none | none | resolution register | achieved
SCM | number of SCM deviation reports submitted to municipal manager (reduction of number of deviations ) | n/a |  | 9 | Maximum of 1 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 30 September 2021 | 0 Maximum of SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 30 September 2021 | none | none | Signed deviation report | achieved
Audit | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year | n/a |  | Qualified audit opinion | n/a | n/a | n/a | n/a | n/a | n/a
| % Internal Audit Findings resolved per quarter as per the Audit Plan | n/a |  | 92% | 100% Internal Audit Findings resolved per quarter as per the Audit Plan by 30 September 2021 | 80% Internal Audit Findings resolved per quarter as per the Audit Plan by 30 September 2021 | development of ward based plan still in progress as we are still benchmarking with other municipalities | to finalise the plan in the next quarter | Quarterly IA follow up report | not achieved
Risk management | % execution of identified risk management plan within prescribed timeframes per quarter | n/a |  | 100% | 25% execution of identified risk management plan within prescribed timeframes per quarter by 30 September 2021 | 40% execution of identified risk management plan within prescribed timeframes per quarter by 30 September 2021 | none | none | Quartely Risk assessent reports | achieved
M.M KGWALE | [7 empty] | DATE
MUNICIPAL MANAGER