## COVER PAGE
ELIAS MOTSOALEDI LOCAL MUNICIPALITY
2017/2018 3rd Quarter Performance Report
A RE BELEGANENG

## SUMMARY
3rd QUARTER PERFORMANCE REPORT
1. Introduction
The Service Delivery and Budget Implementation Plan provides the basis for measuring performance in service delivery against the end of the year targets and implementing the budget. In addition, the SDBIP creates a line of accountability from senior management to all employees. The SDBIP convert the needs of communities into measurable performance measures, indicators and targets.
The SDBIP explicitly defines lines of accountability and responsibility. The Municipal Performance targets are monitored on quarterly basis and as envisaged in the SDBIP are then cascaded to individual managers and will form the basis of the quarterly performance coaching sessions.
2. Executive Summary
The table below represents the institutional performance for the 3rd Quarter per department:
Key Performance Area | departments | Total annual KPI | Total 3rd quarter target | Achieved KPIs | Not achieved KPIs | not applicable | Zero weighted | Total Percentage achieved %
1 | Development planning | 15 | 9 | 8 | 1 | 6 | 0 | 89%
2 | Executive support | 10 | 6 | 4 | 2 | 4 | 0 | 67%
3 | Corporate services | 9 | 6 | 4 | 2 | 3 | 0 | 67%
4 | Municipal Managers' office | 11 | 7 | 4 | 3 | 4 | 0 | 57%
5 | Budget and treasury | 13 | 5 | 4 | 1 | 8 | 0 | 80%
6 | Community services | 10 | 7 | 6 | 1 | 3 | 0 | 86%
7 | Infrastructure | 44 | 34 | 23 | 11 | 6 | 4 | 68%
| TOTAL | 112 | 74 | 53 | 21 | 34 | 4 | 72%
The table below represents the institutional performance for the 3rd Quarter per Key Performance Area:
Key Performance Area | Key Performance Area | Total No. of Set Targets | Total No. of Achieved targets | No. of Targets Not Achieved | % Achieved Targets
1 | Spatial Rationale | 5
2 | Institutional Development & Transformation | 3
3 | Local Economic Development | 4
4 | Basic Service Delivery | 34
5 | Financial Management & Viability | 8
6 | Good Governance & Public Participation | 5
| Total | 59 | 0 | 0 | 65%

## Planning
DEVELOPMENT PLANNING DEPARTMENT
KPA 1: SPATIAL DEVELOPMENT ANALYSIS AND RATIONALE
Strategic Goal: Integrated Human Settlement
Strategic Objective | Programme | KPI | Budget Source | Adjustment budget | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  | Evidence | Achieved / Not achieved
[7 empty] | 3rd Qtr Target | Progress to date | Challenges | Remedial Action
To provide a systematic integrated spatial / land development policy | Land Use Management | Number of informal settlements targeted for upgrading (Zuma Park) | 500000 | 500000 |  | 5 | N/A | N/A | N/A | N/A | N/A | N/A
|  | % Development of a Spatial Development Framework | 500000 | 461000 |  | New | 50% Draft SDF | 50% Draft SDF in place | none | none | 3rd Qtr Draft SDF | achieved
|  | % of Site demarcation projects completed (Ba-Kopa, Ntwane, Ga-Matlala Lehwelere) | 1000000 | 1000000 |  | 50% | n/a | n/a | n/a | n/a | n/a | n/a
|  | % projects implemented based on SPLUMA | 300000 | 300000 |  | 50% | n/a | n/a | n/a | n/a | n/a | n/a
To provide a systematic integrated spatial / land development policy | Land Use Management | % of land use applications received an processed within 90 days | n/a | n/a |  | 100% | 100% | 100% applications received and processed within 90 days | none | none | Land use application register | achieved
Increase regularisation of built environment | Compliance with National building regulations | % of new building plans of less than 500 square metres assessed within 10 days of receipt of plans | n/a | n/a | n/a | 100% | 100% | 100% of new building plans assessed within 10 days | none | none | Building plans application register | achieved
|  | % of new building plans of more than 500 square meters assessed within 28 days of receipt of plans | n/a | n/a | n/a | 100% | 100% | 100% of new building plans assessed within 28 days | none | none | Building plans application register | achieved
|  | % of inspections conducted on building construction with an approved plan to ensure compliance with National Building Regulations and Building Standards | n/a | n/a | n/a | 100% | 100% | 100% % of inspections conducted | none | none | Inspection report | achieved
KPA 3: LOCAL ECONOMIC DEVELOPMENT
Strategic Goal: Growing Inclusive Economy
Strategic Objective | Programme | KPI | Budget Source | Adjustment budget | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  | Evidence | Achieved / Not achieved
[7 empty] | 3rd Qtr Target | Progress to date | Challenges | Remedial Action
To facilitate economic growth and sustainable job creation | EPWP | Number of job opportunities provided through EPWP grant by 30 June 2018 (GKPI) | EPWP grant | EPWP grant | EPWP grant | 451 | n/a | n/a | n/a | n/a | n/a | n/a
| Economic growth and development | Number of networking events held by 30 June 2018 | opex | opex | opex | new | n/a | n/a | n/a | n/a | n/a | n/a
|  | Number of SMME’s and Co-operatives capacity building workshops held by 30 June 2018 | Opex | Opex | Opex | new | 3 | 3 capacity building workshops held | none | none | Reports and attendance registers | achieved
|  | Review of LED Strategy | 500 | 500 | 0 | 1 | 1 | no progress | non reactive bidders delays appointment | re-advertisement to be done | Approved LED strategy and council resolution | not achieved
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic Goal: Sound Governance
Strategic Objective | Programme | KPI | Budget Source | Adjustment budget | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  | Evidence | Achieved / Not achieved
[7 empty] | 3rd Qtr Target | Progress to date | Challenges | Remedial Action
To create a culture of accountability and transparency | Audit | Obtain an Unqualified Auditor General opinion for the 2017/18 financial year | n/a | n/a | n/a | Qualified Opinion | n/a | n/a | n/a | n/a | n/a | n/a
|  | % of Auditor General matters resolved as per the approved audit action plan by 30 June 2018 (Dev. Planning Dept.) | n/a | n/a | n/a | New | 50% | 50% | none | none | Audit action plan | achieved
| Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter (Dev. Planning Dept.) | n/a | n/a | n/a | 90% | 75% | 80% | none | none | Quarterly risk assessment report | achieved

## Corporate Services
CORPORATE SERVICES DEPARTMENT
KPA 2: INSTITUTIONAL DEVELOPMENT AND MUNICIPAL TRANSFORMATION
Strategic Goal: Capacitated and Effective Human Capital
Strategic Objective | Programme | KPI | Budget Source | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  | Evidence | Achieved / Not achieved
[6 empty] | 3rd Qtr Target | Progress to date | Challenges | Remedial Actions
To attract, develop and retain ethical and best human capital | Organizational Development | Number of people from employment equity target groups employed in the three highest level of management in compliance with a municipality’s approved employment equity plan (GKPI) | Opex | Opex | 0 | 3 | 6 people from employment equity target groups employed in the three highest level of management. GE Kegopotsemang, RM Maredi, MM Kgwale, Matlala MV (Manager Licence), Maboa JM and Matumane ND | N/A | N/A | Appointment letters | Target Exceeded
|  | % of budget spent implementing the Workplace Skills Plan by the 30 Jun 2018 (GKPI) | Opex | Opex | 1% | N/A | N/A | N/A | N/A | N/A | N/A
|  | Submission of Review ICT master plan to council by 30 June 2018 | n/a | n/a | 1 | 1 | 0 ICT Master Plan not reviewed. | Focus & prioritisation was on reviewing policies from which there were lots of audit queries. | ICT Master Plan shall be reviewed in the next (Q4) quarter. | Council resolution | Target Not Achieved
|  | Review organizational structure and align to the IDP and Budget by 30 June 2018 | Opex | Opex | 1 | N/A | N/A | N/A | N/A | N/A | N/A
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic Goal: Sound Governance
Strategic Objective | Programme | KPI | Budget Source | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  | Evidence | Achieved / Not achieved
[6 empty] | 3rd Qtr Target | Progress to date | Challenges | Remedial Actions
To create a culture of accountability and transparency | Audit | Obtain an Unqualified Auditor General opinion for the 2016/17 financial year | n/a | n/a | Qualified Opinion | N/A | N/A | N/A | N/A | N/A | N/A
|  | % of Auditor General matters resolved as per the approved audit action plan by 30 June 2018 (Corporate Serv. Dept.) | n/a | n/a | New | 50% | 53% (8/15) of Auditor General matters addressed / resolved. | N/A | N/A | Audit action plan | Target Exceeded
| Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter (Corporate Serv. Dept.) | n/a |  | 90% | 75% | 76% Risk Management Plan Action | N/A | N/A | Quarterly risk assessment report | Target Exceeded
CAPITAL PROJECTS
Ward No. | Project | Strategic Objective | key performance indicator | Original Budget R 000's 2017-18 | Adjustment Budget R 000's 2017-18 | Expenditure | Audited Baseline 2015/16 | 3rd quarter | Progress to date | Challenges | Remedial Actions | Evidence | Achieved / Not achieved
n/a | furniture | Improved efficiency and effectiveness of the municipal administration | % Purchase of furniture | 200000 | 500000 | 188500 | 100% | 100% Purchase of furniture | Service provider was appointed on 27th March 2018 | Insufficient funds which led to budget adjustment being done. | Delivery of purchased furniture in the next quarter (Q4) | delivery note | Target Not Achieved
n/a | computer equipment | Improved efficiency and effectiveness of the municipal administration | % Purchase of computer equipment | 300000 | 800000 | 307562.8 | 100% | 100% Purchase of computer equipment | 100% (8/8) computer equipments purchased | Concerns of laptop slownessness received. | ICT Unit requested to invesitigate causes of laptop slownessness. | delivery note | Target Achieved

## Office of MM
OFFICE OF MUNICIPAL MANAGER
KPA 2: INSTITUTIONAL DEVELOPMENT AND MUNICIPAL TRANSFORMATION
Strategic Goal: Capacitated and Effective Human Capital
Strategic Objective | Programme | KPI | Budget Source | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  |  | Achieved / Not achieved
[6 empty] | 3rd Qtr target | Progress to date | Challenges | Remedial action | Evidence
Improved efficiency and effectiveness of the Municipal Administration | Performance Management | % of KPIs and projects attaining organisational targets (total organisation) by 30 June 2018 | Opex | opex | 71% | 75% | 72% | Operational expenditure understated as they reflect R0,00 actuals and 97/114 Auditor General quiries still in progress | To be address at year end in the Annual Financial Statements | Performance report | Not achieved
|  | Final SDBIP approved by Mayor within 28 days after approval of Budget | n/a | n/a | 1 | n/a | n/a | n/a | n/a | n/a | n/a
KPA 3: LOCAL ECONOMIC DEVELOPMENT
Strategic Goal: Growing Inclusive Economy
Strategic Objective | Programme | KPI | Budget Source | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  |  | Achieved / Not achieved
[6 empty] | 3rd Qtr target | Progress to date | Challenges | Remedial action | Evidence
To facilitate economic growth and sustainable job creation | EPWP | Grant agreement signed between EMLM and dept. of public works stipulating the EPWP targets | n/a | n/a | new | n/a | n/a | n/a | n/a | n/a | n/a
KPA 5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Goal: Sustainable Financial Viability
Strategic Objective | Programme | KPI | Budget Source | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  |  | Achieved / Not achieved
[6 empty] | 3rd Qtr target | Progress to date | Challenges | Remedial action | Evidence
To implement sound Financial management practices | Expenditure | % spend of the Total Operational Budget excluding non-cash items by the 30 June 2018 | Opex | Opex | 91% | 75% | 84.52% | None | None | Section 71 report | Achieved
|  | Remuneration (Employee Related Costs and Councillors Remuneration) as % of Total Operating Expenditure per quarter | Opex | Opex | New | <39% | 44.91% | Total expenditure understated as they reflect R0,00 actuals to date | Ensuring that monthly depreciation and debt impairment actuals are calculated on a monthly basis to avoid understatement of total operating expenditure. | Section 71 report | Not achieved
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic Goal: Sound Governance
Strategic Objective | Programme | KPI | Budget Source | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  |  | Achieved / Not achieved
[6 empty] | 3rd Qtr target | Progress to date | Challenges | Remedial action | Evidence
To strengthen participatory governance within the community | Good Governance and oversight | Submission of Final audited consolidated Annual Report to Council on or before end of January 2018 | n/a | n/a | 1 | 1 | 1 | None | None | Council resolution | Achieved
|  | % of Council meetings resolutions resolved within the prescribed timeframe (3 months) | n/a | n/a | 50% | 100% | 100% | None | None | Council resolution register | Achieved
| IDP Development | Final IDP tabled and approved by Council by the 31 May 2018 | n/a | n/a | 1 | N/A | N/A | N/A | N/A | N/A | N/A
To create a culture of accountability and transparency | Audit | Obtain an Unqualified Auditor General opinion for the 2016/17 financial year | n/a | n/a | Qualified Opinion | n/a | n/a | n/a | n/a | n/a | n/a
|  | % of Auditor General matters resolved as per the approved audit action plan by 30 June 2018 (Total organisation) | n/a | n/a | New | 50% | 28% | The processes to compile complete evidence of work done to resolve AG findings is still in progress | Actions still in progress to be addressed at year end in AFS | Audit action plan | not achieved
| Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter (Total organization) | n/a | n/a | 90% | 75% | 78% | The independent risk chairperson still to be appointed and few officials signed declaration of conflict of interest | The chairperson of risk committee to be appointed in the fourth quarter | Quarterly risk assessment report | Achieved

## Infrastructure
INFRASTRUCTURE DEPARTMENT
KPA 3: LOCAL ECONOMIC DEVELOPMENT
Strategic Goal: Growing Inclusive Economy
Strategic Objective | Programme | KPI | Budget Source | Adjustment budget | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  |  | Achieved / Not achieved
[7 empty] | 3rd Qtr target | Progress to date | Challenges | Remedial action | Evidence
To facilitate economic growth and sustainable job creation | EPWP | Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes | MIG, INEP | MIG, INEP |  | 451 | 400 | 384 | Most of our projects are completed and the municipality is experiencing challenges in increasing the job opportunities | To increase the job creation through roads maintenance projects | List of approved appointees | Not achieved
KPA 4 - BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Strategic Goal: Accessible and Sustainable Infrastructure and Basic Services
Strategic Objective | Programme | KPI | Budget Source | Adjustment budget | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  |  | Achieved / Not achieved
[7 empty] | 3rd Qtr target | Progress to date | Challenges | Remedial action | Evidence
Reduction in the level of Service Delivery backlogs | Electricity | % of households with access to basic levels of electricity by the 30 June 2018 (GKPI) | INEP | 600000 |  | 100% | n/a | n/a | n/a | n/a | n/a | n/a
|  | % development of lighting master plan | opex | 600000 |  | New | 60% collection of data | 0% appointment stage | delay in developing terms of reference | to fast track the appointment of service provider | advertisment | Not achieved
|  | Number of additional households living in formal areas provided with electricity connections | INEP 15 000 000 | INEP 15 000 000 |  | New | n/a | n/a | n/a | n/a | n/a | n/a
| Roads and storm water | KMs of new paved roads to be built | MIG | MIG |  | 11.6km | n/a | n/a | n/a | n/a | n/a | n/a
|  | KMs of roads resurfaced/rehabilitated/resealed | MIG | MIG |  | New | n/a | n/a | n/a | n/a | n/a | n/a
|  | % Development of roads master plan and maintenance plan | opex | 1500000 | 443653.49 | New | 60% submission of draft roads policy to be adopted by council | 60% draft roads policy | None | None | Draft Roads Policy | Achieved
|  | Road signs, main holes, temporary bridges and sign boards | 0 | 500000 | 0 | new | 50% delivery of road furniture | 0% The RFQ for road signs has been submitted to SCM, awaiting for evaluation | Slow turnaround time in procurement process | Improve the turnaround time for procurement process | None | Not achieved
KPA 5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Goal: Sustainable Financial Viability
Strategic Objective | Programme | KPI | Budget Source | Adjustment budget | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  |  | Achieved / Not achieved
[7 empty] | 3rd Qtr target | Progress to date | Challenges | Remedial action | Evidence
Reduction in the level of Service Delivery backlogs | Project Management | % development of capital project implementation plan and submit to Municipal Manager for approval by 30 June 2018 | Opex | Opex | Opex | New | n/a | n/a | n/a | n/a | n/a | n/a
|  | % spending on MIG funding by the 30 June 2018 | MIG | MIG | MIG | 100% | 75% | 73% | Actual spending is 86% of the original allocation, but due to the additional allocation of R11mil the spending dropped | Service providers to submit payment certificates for work done | MIG monthly reports | Not achieved
|  | % development of roads and lighting master plan (Zero weighted. Projects separated for proper reporting) | 2000000 |  |  | New | 75% Data collection | (Zero weighted. Projects separated for proper reporting) | (Zero weighted. Projects separated for proper reporting) | (Zero weighted. Projects separated for proper reporting) | (Zero weighted. Projects separated for proper reporting) | (Zero weighted. Projects separated for proper reporting)
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic Goal: Sound Governance
Strategic Objective | Programme | KPI | Budget Source | Adjustment budget | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  |  | Achieved / Not achieved
[7 empty] | 3rd Qtr target | Progress to date | Challenges | Remedial action | Evidence
To create a culture of accountability and transparency | Audit | Obtain an Unqualified Auditor General opinion for the 2016/17 financial year | n/a | n/a | n/a | Qualified Opinion | n/a | n/a | n/a | n/a | n/a | n/a
|  | % of Auditor General matters resolved as per the approved audit action plan by 30 June 2018 (Infrastructure Dept.) | n/a | n/a | n/a | New | 50% | 50% (two issues were raised: 1 completed and 1 in progress) | None | None | Audit action plan | Achieved
| Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter (Infrastructure Dept.) | n/a | n/a | n/a | 90% | 75% | 67% | still waiting for Eskom to submit quorations for feasibility % | to engage with Eskom | Quarterly risk assessment report | Not achieved

## Infra projects
INFRASTRUCTURE CAPITAL PROJECTS
Ward No. | Project | Strategic Objective | key performance indicator | Original Budget R 000's 2017-18 | Adjustment budget R 000's 2017-18 | Expenditure | Audited Baseline 2015/16 | 3rd quarter | Progress to date | Challenges | Remedial action | Evidence | Achieved / Not achieved
25 | Electrification of households at Makaepea village | Reduction in the level of service delivery backlogs | % electrification of households in makaepea | 710526 | 3912755 | 1341273.77 | new | 75% construction (Pole planting and cabling) | 100% Complete and energized | There are remaining 369 households in Makaepea to be electrified for total cost of R3,7mil | Funds to be availed in the next financial year to electrify the remaining households | Completion Certificate | Achieved
| Electrification of households at Thambo village (extension) | Reduction in the level of service delivery backlogs | % electrification of households in Thambo village (extention) | 1515789 | 1515789 | 1424320.42 | new | 75% construction (Pole planting and cabling) | 100% complete and energized | There are remaining 1112 households in Tambo New Town to be electrified for a total cost of R15mil | Funds to be availed in the next financial year to electrify the remaining households | Completion Certificate | Achieved
14 | Electrification of households at Masakaneng | Reduction in the level of service delivery backlogs | % electrification of households in Masakaneng | 4122807 | 515722 | 568385.53 | new | n/a | 70% - contractor busy with stringing | None | None | Progress report | n/a
9 | Electrification of households at Jabulani D3 | Reduction in the level of service delivery backlogs | % electrification of households in Jabulani D3 | 1010526 | 1010526 | 592774.73 | new | 75% construction (Pole planting and cabling) | 100% Complete and energized | None | None | Completion Certificate | Achieved
21 | Electrification of households at Jerusalema | Reduction in the level of service delivery backlogs | % electrification of households in Jerusalema | 963158 | 116228 | 118776.92 | new | 75% construction (Pole planting and cabling) | 100% Complete and energized | None | None | Completion Certificate | Achieved
All wards | Designs for electrification of villages | Reduction in the level of service delivery backlogs | % development of electrification designs | 877193 | 449812 | 449342.1 | New | 100% detailed designs completed | 100% designs completed | None | None | Detailed Design Report | Achieved
4 | Electrification of household at waalkraal A | Reduction in the level of service delivery backlogs | % electrification of households at waalkraaL A | 2184211 | 2315795 | 2315616.08 | new | 75% construction (Pole planting and cabling) | 100% Complete and energized | None | None | Completion Certificate | Achieved
8 | Electrification of household at Elandsdoorn A | Reduction in the level of service delivery backlogs | % electrification of households at Elandsdoorn A | 328947 | 851974 | 325298.96 | new | 75% construction (Pole planting and cabling) | 100% Complete and energized | None | None | Completion Certificate | Achieved
18 | Electrification of households at Matsitsi | Reduction in the level of service delivery backlogs | % electrification of households in matsitsi | 1444737 | 2469293 | 2303816.24 | new | 75% construction (Pole planting and cabling) | 100% Complete and energized | None | None | Completion Certificate | Achieved
20 | Hlogotlou street and storm water control | Reduction in the level of service delivery backlogs | % construction of Hlogotlou street and storm water control | 3333333 | 5843790 | 4388425.21 | 100% | 75% Construction of street and storm water control (Trenching and pitching) | 88% construction, contractor busy with installation of kerbs | None | None | Progress report | Achieved
21 | Kgaphamadi construction of bus road, bridge and stormwater control PH 1C (1km) | Reduction in the level of service delivery backlogs | % construction of Kgaphamadi bus road, bridge and stormwater control PH 1C (1km) | 5 263 158 | 5 263 158 | 5273497.62 | 100% | 75% progress (Base and Surfacing completed) | 100% complete | Stormwater Control problem which might affect the road. | The municipality to prioritise storm water control in the next phase of the project | Completion Certificate | Achieved
26 | Kgoshi-Rammupudu construction of access road and storm water control PH 1C | Reduction in the level of service delivery backlogs | % construction of kgoshi Rammupudu road | 8 924 272 | 8836424 | 8341581.13 | 100% | 75% progress (Base and Surfacing completed) | 100% complete with the initial scope, currently busy with the additional works | The remaining length of the road is 2,1km and remaining budget will only do 1,3km. Community disrupting the completion of the additional works at phase 1C with reasons relating to subcontracting | The municpality to apply for MIG extra funding. An intervention meeting was held and an advert for subcontracting works was issue to the community but was rejected by some members | Progress report | Achieved
25 | Kgoshi-Matsepe construction of access road and storm water control PH 1A (Zero weighted. Project not registered with MIG) | Reduction in the level of service delivery backlogs | % construction of kgoshi Matsepe road | 2710526 | 0 | 0 | new | n/a | (Zero weighted. Project not registered with MIG) | (Zero weighted. Project not registered with MIG) | (Zero weighted. Project not registered with MIG) | (Zero weighted. Project not registered with MIG) | (Zero weighted. Project not registered with MIG)
10 | Kgoshi Mathebe Road Construction (Zero weighted. Project not registered with MIG) | Reduction in the level of service delivery backlogs | % construction of Mathebe road | 3 333 333 | 0 | 0 | New | n/a | (Zero weighted. Project not registered with MIG) | (Zero weighted. Project not registered with MIG) | (Zero weighted. Project not registered with MIG) | (Zero weighted. Project not registered with MIG) | (Zero weighted. Project not registered with MIG)
25 | Rehabilitation of dikgalaopeng road and storm water control | Reduction in the level of service delivery backlogs | % rehabilitation of dikgalaopeng road and storm water control | 877193 | 1754386 | 0 | new | 75% progress (Base and Surfacing completed) | 5% contractor busy with site establishment | Project behind schedule | To fast track the progress through estabilishing more teams on site | None | Not achieved
25 | Rehabilitation of Ramogwerane to Nkadimeng road and storm water | Reduction in the level of service delivery backlogs | % Rehabilitation of Ramogwerane to Nkadimeng road and storm water | 877193 | 877193 | 0 | new | 75% progress ( Base and Surfacing completed) | Tender Stage | The tender was re-advertersied twice due to non competative biding | To fast track the procurement processes | None | Not achieved
13 | Groblersdal roads and streets | Reduction in the level of service delivery backlogs | % maintenance of Groblersdal roads and streets | 2631579 | 5631579 | 0 | New | 75% maintenance of Groblersdal roads and streets | 15% complete, contractor busy with clearing | Project behind schedule | To fast track the progress through estabilishing more teams on site | None | Not achieved
19 | Mathula construction of road and storm water control PH 1B | Reduction in the level of service delivery backlogs | % construction of Mathula road and storm water control | 8 410 581 | 7511881 | 5569290.97 | 100% | 75% progress ( Base and Surfacing completed) | 90% complete, busy with finishes | Contractors Site Management Systems Inadequate. Variation Order for road intersection to be raised | Intervention Meeting held by the Municipality with the Engineer and the Contractor to resolve the issue. The Engineer was requested to submit the Variation Order for approval | Progress report | Achieved
14 | Naganeng construction of bus road and storm water control PH 1A | Reduction in the level of service delivery backlogs | % construction of Naganeng road and storm water control | 10526316 | 22378603 | 14760544.16 | new | 60% progress (Base and Surfacing completed) | 98% complete, busy with road markings for 3.8km road | None | None | Progress report | Achieved
16 | Zaaiplaas construction of JJ road and storm water control PH 1C | Reduction in the level of service delivery backlogs | % construction of JJ road and storm water control | 4385965 | 5132310 | 4917365.21 | 100% | 75% progress (Base and Surfacing completed) | 100% complete | The remaining length of the road is 2,1km and remaining budget will only do 0,6km. | The municpality to apply for MIG extra funding to finalise the project. | Completion Certificate | Achieved
9 | Tambo road construction | Reduction in the level of service delivery backlogs | % construction of Tambo road | 5 445 849 | 5086346 | 5196943.86 | New | 75% progress (Base and Surfacing completed) | 100% complete | None | None | Completion Certificate | Achieved
31 | Motetema street upgrade | Reduction in the level of service delivery backlogs | % upgrading of Motetema street | 877193 | 877193 | 0 | New | 75% progress (Base and Surfacing completed) | Tender Stage | The tender was re-advertersied twice due to non competative biding | To fast track the procurement processes | None | Not achieved
| Marapong bridge | Reduction in the level of service delivery backlogs | % construction of Marapong bridge | 0 | 1584474 | 1159983.07 | 50% | 100% | 100% complete | None | None | Practical Completion Certificate | Achieved
13 | Klip and Kanaal | Reduction in the level of service delivery backlogs | % construction of Klip and Kanaal | 0 | 186362 | 186362.28 | 50% | 200% | 100% complete | None | None | Completion Certificate | Achieved
n/a | Machinery and equipment | Reduction in the level of service delivery backlogs | % purchase of machinery and equipment | 500000 | 1100000 | 0 | New | 100% purchase of machinery and equipment | 80% - The service provider has been appointed to procure fault locator for electricity | None | None | None | Not achieved
n/a | Vehicles (Zero weighted) | Reduction in the level of service delivery backlogs | number of vehicles to be purchased | 700000 | 0 | 0 | new | n/a | (Zero weighted) | (Zero weighted) | (Zero weighted) | (Zero weighted) | (Zero weighted)
13 | Development of workshop | Reduction in the level of service delivery backlogs | % development of workshop | 3947368 | 1436911 | 104983.2 | 25% | 75% Development of Workshop (fencing completed) | Tender Stage | Project delayed due to insufficient funds | Project to be advertised during third quarter | None | Not achieved
2016/2017 Rolled over projects
Ward No. | Project | Strategic Objective | key performance indicator | Original Budget R 000's 2017-18 | Adjustment budget R 000's 2017-18 | Expenditure | Audited Baseline 2015/16 | 3rd quarter | Progress to date | Challenges | Remedial action | Evidence | Achieved / Not achieved
30 | electrification of Tshehla Trust | Reduction in the level of service delivery backlogs | % electrification of households at Tshehla trust | 0 | 165789 | 165789.47 | 50% | 100% | 100% complete | None | None | Completion certificate | Achieved
13 | Laersdrift road | Reduction in the level of service delivery backlogs | % construction of Laersdrift road | 0 | 322807 | 0 | 50% | 100% | 100% complete | Non-payment of CLO and service providers | The municipality has instructed the Engineer to deduct the money from Contractor's claim, and they will be paid through cession. | Practical Completion certificate | Achieved
| Mogaung road | Reduction in the level of service delivery backlogs | % construction of Mogaung road | 0 | 5197354 | 3916950.57 | 50% | 80% | 98% contractor busy with snaglisted items | None | None | Practical Completion Certificate | Achieved
20 | Multipurpose sports (Hlogotlou stadium) | Reduction in the level of service delivery backlogs | % construction of Hlogotlou stadium | 0 | 8078532 | 6972533.59 | 50% | 100% | 98% contractor busy with snaglisted items | Delays on electrical works | The contractor was instructed to complete the outstanding works | Practical Completion Certificate | Achieved

## Community Services
COMMUNITY SERVICES
KPA 4 – BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Strategic Goal: Accessible and Sustainable Infrastructure and Basic Services
Strategic Objective | Programme | KPI | Budget Source | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  |  | Achieved / Not achieved
[6 empty] | 3rd Qtr target | Progress to date | Challenges | Remedial action | Evidence
Reduction in the level of Service Delivery backlogs | Waste management | % of households with access to a minimum level of basic waste removal by 30 June 2018 (once per week) (GKPI) | Opex |  | New | N/A | N/A | N/A | N/A | N/A | N/A
To facilitate promotion of education upliftment within communities | Education/ Libraries | Number of initiatives held to promote library facilities by 30 June 2018 | n/a |  | 4 | 3 | 3 | None | None | Attendance register and minutes | Achieved
To ensure communities are contributing towards climate change and reduction of carbon footprint | Environmental management | Number of waste minimization projects initiated by 30 June 2018 (Environmental awareness programmes) | Opex |  | 4 | 3 | 3 | None | None | Reports and attendance registers | Achieved
Increase the accessibility of emergency services to the community | Disaster management | Number of disaster awareness campaigns conducted by 30 June 2018 | Opex |  | 8 | 3 | 3 | None | None | Attendance register and minutes | Achieved
Facilitate safe and secure neighborhoods | Safety and security | Number of community safety forum meeting held | n/a |  | New | 3 | 3 | None | None | Attendance register and minutes | Achieved
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic Goal: Sound Governance
Strategic Objective | Programme | KPI | Budget Source | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  |  | Achieved / Not achieved
[6 empty] | 3rd Qtr target | Progress to date | Challenges | Remedial action | Evidence
To create a culture of accountability and transparency | Audit | Obtain an Unqualified Auditor General opinion for the 2016/17 financial year | n/a |  | Qualified Opinion | N/A | N/A | N/A | N/A | N/A | N/A
|  | % of Auditor General matters resolved as per the approved audit action plan by 30 June 2018 (CS Dept.) | n/a |  | New | 50% | 50% | None | None | Audit action plan | Achieved
| Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter (CS Dept.) | n/a |  | 90% | 75% | 83% | None | None | Quarterly risk assessment report | Achieved
CAPITAL PROJECTS
Ward No. | Project | Strategic Objective | key performance indicator | Original Budget R 000's 2017-18 | adjustment Budget R 000's 2017-18 | Audited Baseline 2015/16 | 3rd Qtr target | Progress to date | Challenges | Remedial action | Evidence | Achieved / Not achieved
All wards | Grass cutting Industrial Machine (lawnmower, chain saw, brush cutters, pole | Reduction in the level of service delivery backlogs | number of grass cutting industrial machine purchased | 400000 | 400000 | new | n/a | n/a | n/a | n/a | n/a | n/a
13 | upgrading of driving license testing centre | Reduction in the level of service delivery backlogs | % upgrading of driving licence testing centre | 500000 | 500000 | 50% | 100% upgraded driving license testing centre | Re-advert done and Evaluation had their sitting on the 04/04/2018 | It was since interrrupted by Community Members | Re-advert | Q3 completion certificate | Not Achieved

## Budget & Treasury
BUDGET AND TREASURY DEPARTMENT
KPA 4 – BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Strategic Goal: Improved Social Well-Being
Strategic Objective | Programme | KPI | Budget Source | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  |  | Achieved / Not achieved
[6 empty] | 3rd Qtr target | Progress to date | Challenges | Remedial action | Evidence
To provide free basic services to registered indigents | Indigents | % of (indigents) households with access to free basic electricity services by 30 Jun 2018 (GKPI) | opex |  | 14% | N/A | N/A | N/A | N/A | N/A | N/A
|  | Number of additional households provided with access to Free Basic Electricity | opex |  | New | 150 | 1184 indigents were submitted to Eskom for configuration during the period July to December 2017 and awaiting the distributor to finalise setup for FBE distribution. | Delay in Eskom to configure the list of indigents submitted by the municipality for registration. | Organise a meeting with Eskom to unlock the challenges encountered. Establish the indigent management committee to regulary meet and address the challenges in indigent management. | ESKOM beneficiary register | achieved
KPA 5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Goal: Sustainable Financial Viability
Strategic Objective | Programme | KPI | Budget Source | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  |  | Achieved / Not achieved
[6 empty] | 3rd Qtr target | Progress to date | Challenges | Remedial action | Evidence
To implement sound Financial management practices | Financial management | Cost coverage ratio by the 30 June 2018 (GKPI) | N/A |  | 2:01 | N/A | N/A | N/A | N/A | N/A | N/A
| Revenue | % outstanding service debtors to revenue by the 30 June 2018 (GKPI) | N/A |  | 13% | N/A | N/A | N/A | N/A | N/A | N/A
|  | % Debt coverage ratio by the 30 June 2018 (GKPI) | N/A |  | 191% | N/A | N/A | N/A | N/A | N/A | N/A
| Compliance with MFMA legislation | Submission of MTRE Budget to Council 30 days before the start of the new FY | N/A |  | 1 | N/A | N/A | N/A | N/A | N/A | N/A
Compliance to MFMA legislation | Legislative compliance | Audited Annual Financial Statements (AFS) and Audit report submitted to Council by December 2017 | N/A |  | 1 | N/A | N/A | N/A | N/A | N/A | N/A
| SCM | number of monthly SCM deviation reports submitted to the Municipal Manager | N/A |  | 12 | 9 | 9 Monthly deviation reports for January to March were prepared and submitted to the Accounting Officer | None | None | Deviation register | Achieved
To implement sound financial management practices | Expenditure | % Payment of creditors within 30 days | Opex and capex budget |  | 100% | 100% | 100% All creditors paid within 30 days in third quarter | None | None | Creditors age analysis | Achieved
| Assets management | Number of assets verification reports submitted to Municipal Manager by 30 June 2018 | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic Goal: Sound Governance
Strategic Objective | Programme | KPI | Budget Source | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  |  | Achieved / Not achieved
[6 empty] | 3rd Qtr target | Progress to date | Challenges | Remedial action | Evidence
To create a culture of accountability and transparency | Audit | Obtain an Unqualified Auditor General opinion for the 2016/17 financial year | n/a |  | Qualified Opinion | N/A | N/A | N/A | N/A | N/A | N/A
|  | % of Auditor General matters resolved as per the approved audit action plan by 30 June 2018 (Finance Dept.) | n/a |  | New | 50% | 23% | Unknown properties ,resolution by council to process the writte off of the suspense accounts on VAT and Trade payables. (The journals have been processed and resolution to be attached for audit in August 2018) | The mistatements on the management report as reported in 2017 will be disccussed with the AG for approval of adjustment during 2017/2018 audit. | Audit action plan | Not achieved
| Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter (Finance Dept.) | n/a |  | 90% | 75% | 84% | None | None | Quarterly risk assessment report | Achieved

## Executive support
EXECUTIVE SUPPORT
KPA 4 - BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Strategic Goal: Improved Social Well-Being
Strategic Objective | Programme | KPI | Budget Source | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  |  | Achieved / Not achieved
[6 empty] | 3rd Qtr target | Progress to date | Challenges | Remedial action | Evidence
Facilitate promotion of health and well-being of communities | Transversal programmes | number of Transversal programmes implemented in terms of mainstreaming with respect to HIV/AIDS, Gender, Disabled, Woman and Children Rights by the 30 Jun 2018 | Opex |  | New | 3 | 11 | None | None | Programme and attendance register | achieved
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic Goal: Sound Governance
Strategic Objective | Programme | KPI | Budget Source | Expenditure | Audited Baseline 2015/16 | 2017/2018 |  |  |  |  | Achieved / Not achieved
[6 empty] | 3rd Qtr target | Progress to date | Challenges | Remedial action | Evidence
To strengthen participatory governance within the community | Community Participation | number of quarterly reports submitted to Council in terms of items raised during public participation; within the mandate of Council, that are processed and resolved within (3) months | n/a |  | New | 3 | 2 | Other issues were raised at the end of the 3rd quarter therefore could not be reported on time | Other issues raised to be submitted in the 4th quarter | Council resolution | Not achieved
|  | number of Community Satisfaction Surveys conducted by the 30 Jun 2018 | Opex |  | New | N/A | N/A | N/A | N/A | N/A | N/A
To create a culture of accountability and transparency | MPAC | number of MPAC quarterly reports submitted to council | n/a |  | New | 3 | 2 | project visits were rescheduled for fourth quarter | To be submitted in the fourth quarter | Council resolution | Not achieved
Facilitates promotion of health and well-being of communities | Mayoral programme | number of Mayoral outreach projects initiated by 30 Jun 2018 | 1110000 |  | 14 | N/A | N/A | N/A | N/A | N/A | N/A
| Speakers programme | number of Speaker’s outreach projects initiated by 30 Jun 2018 | 700000 |  | New | 1 | 1 | None | None | Report and Attendance register | Achieved
| MPAC programme | number of MPAC outreach projects initiated by 30 Jun 2018 | 400000 |  | New | 1 | 1 | None | None | Report Attendance register | Achieved
To create a culture of accountability and transparency | Audit | Obtain an Unqualified Auditor General opinion for the 2016/17 financial year | n/a |  | Qualified Opinion | N/A | N/A | N/A | N/A | N/A | N/A
|  | % of Auditor General matters resolved as per the approved audit action plan by 30 June 2018 (Executive Support Dept.) | n/a |  | New | 50% | N/A (The department was not audited in the previous financial year) | N/A | N/A | N/A | N/A
| Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter (Executive Support Dept.) | n/a |  | 90% | 75% | 78% | None | None | Quarterly risk assessment report | Achieved