## COVER PAGE
ELIAS MOTSOALEDI LOCAL MUNICIPALITY
2021 / 2022 Second quarter performance report
A RE BELEGANENG

## summary 01
MID YEAR PERFORMANCE REPORT
1. Introduction
The Service Delivery and Budget Implementation Plan provides the basis for measuring performance in service delivery against the end of the year targets and implementing the budget. In addition, the SDBIP creates a line of accountability from senior management to all employees. The SDBIP convert the needs of communities into measurable performance measures, indicators and targets.
The SDBIP explicitly defines lines of accountability and responsibility. The Municipal Performance targets are monitored on quarterly basis and as envisaged in the SDBIP are then cascaded to individual managers and will form the basis of the quarterly performance coaching sessions.
2. Executive Summary
The table below represents the institutional performance for Mid Year per department:
Key Performance Area | departments | Total 2nd quarter target | Achieved KPIs | Not achieved KPIs | not applicable | Total Percentage achieved %
1 | Development planning | 11 | 10 | 1 |  | 91%
2 | Executive support | 9 | 7 | 2 |  | 78%
3 | Corporate services | 9 | 8 | 1 |  | 89%
7 | Municipal Managers' office | 14 | 13 | 1 |  | 93%
5 | Finance | 7 | 6 | 1 |  | 86%
6 | Community services | 17 | 12 | 1 | 4 | 92%
7 | Infrastructure | 23 | 9 | 13 | 1 | 41%
| TOTAL | 90 | 65 | 20 | 5 | 76%
The table below represents the institutional performance for Mid Year per Key Performance Area:
Key Performance Area Number | Key Performance Area | Total 2nd quarter target | Achieved KPIs | Not achieved KPIs | not applicable | Total Percentage achieved %
1 | Spatial Rationale | 4 | 4 | 0 | 0 | 100%
2 | Institutional Development & Transformation | 8 | 7 | 1 | 0 | 88%
3 | Local Economic Development | 3 | 2 | 1 | 0 | 67%
4 | Basic Service Delivery | 30 | 15 | 10 | 5 | 60%
5 | Financial Management & Viability | 8 | 6 | 2 | 0 | 75%
6 | Good Governance & Public Participation | 18 | 16 | 2 | 0 | 89%
| Total | 71 | 50 | 16 | 5 | 76%

## Planning
DEVELOPMENT PLANNING
KPA 1: SPATIAL DEVELOPMENT ANALYSIS AND RATIONALE
Strategic objectives: To promote intergrated human settlements
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience
Land Use Management | % of land use applications received and processed within 90 days | n/a |  | 100% | 100% of land use applications received and processed within 90 days by 31 December 2021 | 100% of land use applications received and processed within 90 days by 31 December 2021 | none | none | land use application register | achieved
| % of new building plans of less than 500 square metres assessed within 10 days of receipt of plans | n/a |  | 100% | 100% of new buildings plans of less than 500 sqm assessed within 10 days upon receipt of plans by 31 December 2021 | 100% of land use applications received and processed within 90 days by 31 December 2021 | none | none | building plans application register | achieved
| % of new building plans of more than 500 square meters assessed within 28 days of receipt of plans | n/a |  | 100% | 100% of new building plans of more than 500 square meters assessed within 28 days of receipt of plans by 31 December 2021 | 100% of land use applications received and processed within 90 days by 31 December 2021 | none | none | building plans application register | achieved
Compliance with National Building Regulations | % of inspections conducted on building construction with an approved plan to ensure compliance with Sec.6©and 17 (b) of National Building Regulations and Building Standards Act | n/a |  | 100% | 100% of inspections conducted on building construction with an approved plan to ensure compliance with Sec.6©and 17 (b) of National Building Regulations and Building Standards Act by 31 December 2021 | 100% of land use applications received and processed within 90 days by 31 December 2021 | none | none | inspection report | achieved
Strategic objectives: To promote conducive enviroment for economic growth and development
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience
EPWP | Number of job opportunities provided through EPWP grant (GKPI) | EPWP grant |  | 69 | 69 job opportunities provided through EPWP grant by 31 December 2021 (GKPI) | 90 job opportunities provided through EPWP grant by 31 December 2021 (GKPI) | none | none | List of approved appointees | achieved
| Number of SMME’s and Co-operatives capacity building workshops/ training held(LED training) | Opex |  | 12 | 6 SMME’s and Co-operatives capacity building workshops/ training held by 31 December 2021 (LED training) | 12 SMME’s and Co-operatives capacity building workshops/ training held by 31 December 2021 (LED training) | none | none | reports and attendance registers | achieved
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic objectives : To enhance good governance and public participation
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 2nd Qrt Target | Progress to date | Challenges | Reason for Varience
Audit | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year | n/a |  | Qualified audit opinion | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year by 30 November 2021 | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year by 30 November 2021 | none | none | AGSA audit report | achieved
[5 empty] | n/a | n/a | n/a | n/a | n/a | n/a
| % Internal Audit Findings resolved per quarter as per the Audit Plan | n/a |  | 92% | 100% Internal Audit Findings resolved per quarter as per the Audit Plan by 31 December 2021 | 100% Internal Audit Findings resolved per quarter as per the Audit Plan by 31 December 2021 | none | none | Quarterly IA follow up report | achieved
Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter | n/a |  | 100% | 50% execution of identified risk management plan within prescribed timeframes per quarter by 31 December 2021 | 55% execution of identified risk management plan within prescribed timeframes per quarter by 31 December 2021 | none | none | Quartely Risk assessent reports | achieved
KPA 5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Objectives : To improve sound and municipal financial management
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience
SCM | Number of SCM deviation reports submitted to municipa manager (reduction of number of deviations) | n/a |  | 9 | Maximum of 1 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 31 December 2021 | 0 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 31 December 2021 | none | none | Signed deviation report | achieved | achieved
CAPITAL PROJECTS
ward no | Project | key performance indicator | Original Budget R 000's 2021/22 | Expenditure | Audited Baseline 2019/20 | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience | Evidence | Achieved / Not Achieved | Achieved / Not Achieved
13 | Fencing of Game Farm | Fencing of Game Farm | 1100000 | 0 | new | placing of advertisement of service providers by 31 December 2021 | no progress | specifications were developed | to fast track the process of advertisment | copy of advertisement | not achieved

## Corporate Services
CORPORATE SERVICES
KPA 2: INSTITUTIONAL DEVELOPMENT AND MUNICIPAL TRANSFORMATION
Strategic Objectives: To build capabe, responsive, accountable, effective and efficient municipal institutions and administration
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience
employment equity | review of the Employment Equity Plan | n/a |  | new | n/a | n/a | n/a | n/a | n/a | n/a
| Submission of employment equity report to DOL by 31st January 2022 | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
| % of employees with disabilities | n/a |  | new | n/a | n/a | n/a | n/a | n/a | n/a
Skills programme | Number of employees approved for study financial assistance | Opex |  | 0 | n/a | n/a | n/a | n/a | n/a | n/a
WSP | Approval of reviewed WSP (work skills plan) | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
| % of a municipality's payroll budget on training and education of employees | 1% |  | 80% | n/a | n/a | n/a | n/a | n/a | n/a
LLF | Number of LLF meetings held | n/a |  | 9 | 3 LLF meetings held by 31 December 2021 | 4 LLF meetings held: *03/08/2021 *03/09/2021 *13/10/2021 *03/12/2021 | none | none | attendance register and minutes | achieved
ICT | % of reportet ICT incidents resolved | n/a |  | new | 90% - 100% % of reported ICT incidents resolved by 31 December 2021 | 100% (72/72) of reported ICT incidents resolved by 31 December 2021 | none | none | ICT Job Card | achieved
| turnaround time in placing documents and information on the municipal webite | 187020 |  | new | Placement of documents and information on municipal website 5 (five)working days from the date submitted to ICT by 31 December 2021 | Documents and information placed on municipal website within 5(five)working days from the date submitted to ICT by 31 December 2021 | none | none | *Website Register * SITA email confirming placement of documents and information | achieved
| Number of ICT Service Providers Peformance Monitoring and Evaluation meetings held | n/a |  | 4 | 2 ICT Service Providers Peformance Monitoring and Evaluation meetings held by 31 December 2021 | 1 ICT Service Providers Peformance Monitoring and Evaluation meetings held by 09t December 2021 | none | none | Attendance Register and Minutes | achieved
Occupational health and safety (OHS) | % expenditure of uniform and protective clothing | 1000000 |  | new | n/a | n/a | n/a | n/a | n/a | n/a
Occupational health and safety (OHS) | Medical Surveillance conducted | 244165 |  | new | n/a | n/a | n/a | n/a | n/a | n/a
Occupational health and safety (OHS) | First Aid in the Workplace/ Risk Based Primary Emergency Care Training for Health and Safety Committee held | n/a |  | new | n/a | n/a | n/a | n/a | n/a | n/a
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic objectives : To enhance good governance and public participation
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 2nd Qtr target | Progress to date | Challenges | Reason for Varience
Audit | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year | n/a |  | Qualified audit opinion | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year by 30 November 2021 | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year by 30 November 2021 | none | none | AGSA audit report | achieved
| % Auditor General matters resolved as per the approved audit action plan | n/a |  | 87% | n/a | n/a | n/a | n/a | n/a | n/a
| % Internal Audit Findings resolved per quarter as per the Audit Plan | n/a |  | 92% | 100% Internal Audit Findings resolved per quarter as per the Audit Plan by 31 December 2021 | 65% Internal Audit Findings resolved per quarter as per the Audit Plan by 31 December 2021 | None | Action plan implementation date not due | Quarterly IA follow up report | Not Achieved
Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter | n/a |  | 100% | 50% execution of identified risk management plan within prescribed timeframes per quarter by 31 December 2021 | 67% execution of identified risk management plan within prescribed timeframes per quarter by 31 December 2021 | none | none | Quartely Risk assessent reports | achieved
CAPITAL PROJECTS
ward no | Project | key performance indicator | Original Budget R 000's 2021/22 | Expenditure | Audited Baseline 2019/20 | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience | Evidence | Achieved / Not Achieved
n/a | Computer Equipment | % expenditure on computer equipment | 460000 | 459 400 | 100% | 25% minimum expenditure on computer equipment by 31 December 2021 | 99.8% (R459,400 / R460,000) minimum expenditure on computer equipment by 31 December 2021 | New employees' appointment with resultant demand for computer equipment | Consider upward budget adjustment | Expenditure report / screen shot | achieved
KPA 5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Objectives : To improve sound and municipal financial management
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 1st Qtr Target | Progress to date | Challenges | Reason for Varience
SCM | Number of SCM deviation reports submitted to municipa manager (reduction of number of deviations) | n/a |  | 9 | Maximum of 1 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 31 December 2021 | 0 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 31 December 2021 | none | none | Signed deviation report | achieved

## Office of MM
MUNICIPAL MANAGER'S OFFICE
KPA 2 : INSTITUTIONAL DEVELOPMENT AND MUNICIPAL TRANSFORMATION
Strategic Objectives : To build capable, responsive, accountable, effective and efficient municipal institutions and administration
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/2022 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience
Performance Management | % of KPIs and projects attainin organisational targets (total organisation) | n/a |  | 49% | 50% of KPIs and projects attainin organisational targets (total organisation) by 31 December 2021 | 76% of KPIs and projects attainin organisational targets (total organisation) by 31 December 2021 | none | none | performance report | achieved
| Final SDBIP approved by Mayor within 28 days after approval of IDP/ Budget | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
| number of litigations reports created | n/a |  | new | 2 litigations report created by 31 December 2021 | 2 litigations report created by 31 December 2021 | none | none | litigation reports | achieved
KPA 5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Objectives : To improve sound and municipal financial management
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience
Expenditure | % spend of the Total Operational Budget excluding non-cash items | Opex |  | 95% | 55% spend of the Total Operational Budget excluding non-cash items by the 31 December 2021 | 54% (saving) spend of the Total Operational Budget excluding non-cash items by the 31 December 2021 | none | none | Budget report | achieved
Expenditure | Remuneration (Employee Related Costs and Councillors Remuneration) as % of Total Operating Expenditure per quarter | Opex |  | 34% | 25% to 40% Remuneration (Employee Related Costs and Councillors Remuneration) as % of Total Operating Expenditure per quarter by 31 December 2021 | 41% Remuneration (Employee Related Costs and Councillors Remuneration) as % of Total Operating Expenditure per quarter by 31 December 2021 | Non-incorporation of depreciation and asset impairment, including debt impairment and this results in understated operating expenditure | Understatement of operational expenditure | Section 71 report | Not Achieved
SCM | Number of SCM deviation reports submitted to municipa manager (reduction of number of deviations) | n/a |  | 9 | Maximum of 1 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 31 December 2021 | 0 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 31 December 2021 | none | none | Signed deviation report | achieved
KPA 6 : GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic Objectives : To enhance good governance and public participation
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience
Good Governance and oversight | Submission of Final audited (2020-2021) consolidated Annual Report to Council by 31 January 2022 | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
| submisson of annual report oversight report to council by March 2022 | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
| 2021 /2022 IDP review process plan approved by August 2021 |  |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
IDP Development | Final IDP tabled and approved by Council by the 31 May 2022 | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
Audit | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year | n/a |  | Qualified audit opinion | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year by 30 November 2021 | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year by 30 November 2021 | none | none | AGSA audit report | achieved
| % of Auditor General matters resolved as per the approved audit action plan (Total organisation) | n/a |  | 87% | n/a | n/a | n/a | n/a | n/a | n/a
Audit | % Internal Audit Findings resolved per quarter as per the Audit Plan (total organisation) | n/a |  | 92% | 100% Internal Audit Findings resolved per quarter as per the Audit Plan (total organisation) by 31 December 2021 | 100% Internal Audit Findings resolved per quarter as per the Audit Plan (total organisation) by 31 December 2021 | none | none | Quarterly IA follow up report | achieved
Risk Management | Number of risk based internal audits conducted | n/a |  | new | n/a | n/a | n/a | n/a | n/a | n/a
Risk Management | Number of security risk asessment conducted | n/a |  | 4 | 2 security risk asessment conducted by 31 December 2021 | 2 security risk asessment conducted by 31 December 2021 | none | none | Quartely Risk Assessment report | Achieved
| number of project risk assessments conducted | n/a |  | 2 | 2 project risk assessments conducted by 31 December 2021 | 2 project risk assessments conducted by 31 December 2021 | none | none | Quartely Risk assessment report | Achieved
| Number of strategic and operational risk assessment conducted | n/a |  | new | 2 strategic and operational risk assessment conducted by 31 December 2021 | 2 strategic and operational risk assessment conducted by 31 December 2021 | none | none | Assessment report | Achieved
| Number of risk management training conducted | n/a |  | new | 1 risk management training conducted by 31 December 2021 | 1 risk management training conducted by 31 December 2021 | none | none | attendance register | Achieved
| Number of Risk Management reports submitted to the Risk Management Committee per quarter | n/a |  | 4 | 2 Risk Management reports submitted to the Risk Management Committee per quarter by 31 December 2021 | 2 Risk Management reports submitted to the Risk Management Committee per quarter by 31 December 2021 | none | none | Quartely Risk assessment report | Achieved
| Number of quartely Risk Management Committtee meetings convened | n/a |  | 4 | 2 quartely Risk Management Committtee meetings convened by 31 December 2021 | 2 quartely Risk Management Committtee meetings convened by 31 December 2021 | none | none | attendance reigister and minutes | Achieved
Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter (Total organisation) | n/a |  | 100% | 50% execution of identified risk management plan within prescribed timeframes per quarter (Total organisation) by 31 December 2021 | 50% execution of identified risk management plan within prescribed timeframes per quarter (Total organisation) by 31 December 2021 | none | none | Quartely Risk assessment reports | Achieved

## Infrastructure
INFRASTRUCTURE
KPA 3: LOCAL ECONOMIC DEVELOPMENT
Strategic Objectives: To promote conducive enviroment for economic growthe and development
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence
[5 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience |  | Achieved / Not Achieved
EPWP | number of job opportunities created through infrastructure projects (GKPI) | MIG/INEP/EMLM |  | 253 | 160 job opportunities created through infrastructure projects by 31 December 2021 (GKPI) | 102 of job opportunities created through Infrastructure by 31 December 2021 | Only 3 roads construction projects are at implementation stage . Four (04) electrical projects were handed over to contractors in December. Two (02) electrical projects are still on design stage | to continue with appointment as soon as the remaining projects are at implementation stage | List of appointees | not achieved
KPA 4: BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Strategic Objectives: To provide for basic services delivery and sustainable infrastractural development
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22
[5 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience | Evidence | Achieved / Not Achieved
Roads and storm water |  | n/a |  | 120.5km | 60km of gravel municipal roads/streets re-regravelled by 31 December 2021 | 70km of gravel municipal roads/streets re-regravelled by 31 December 2021 | None | None | completion certificates | achieved
KPA 5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Objectives : To improve sound and sustainable municipal financial management
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence
[5 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience |  | Achieved / Not Achieved
Project Management | % spending on MIG funding by the 30 June 2022 | MIG |  | 91% | 50% spending on MIG funding by the 31 December 2021 | 56.18% spending on MIG funding by the 31 December 2021 | None | None | MIG monthly report | achieved
Electricity | % spending on INEP funding by 30 June 2022 | INEP |  | 100% | spending on INEP funding by 31 December 2021 | 4% spending on INEP funding by 31 December 2021 | Late appointment of contractors | Contractors to resume work after the holidays | INEP monthly report | not achieved
SCM | Number of SCM deviation reports submitted to municipa manager (reduction of number of deviations) | n/a |  | 9 | Maximum of 1 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 31 December 2021 | 0 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 31 December 2021 | None | None | Signed deviation report | achieved
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic objectives : To enhance good governance and public participation
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience
Audit | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year | n/a |  | Qualified audit opinion | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year by 30 November 2021 | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year by 30 November 2021 | none | none | AGSA audit report | achieved
| % Auditor General matters resolved as per the approved audit action plan | n/a |  | 87% | n/a | n/a | n/a | n/a | n/a | n/a
| % Internal Audit Findings resolved per quarter as per the Audit Plan | n/a |  | 92% | 100% Internal Audit Findings resolved per quarter as per the Audit Plan by 31 December 2021 | 63% Internal Audit Findings resolved per quarter as per the Audit Plan by 31 December 2021 | None | Action plan implementation date not due | Quarterly IA follow up report | Not Achieved
Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter | n/a |  | 100% | 50% execution of identified risk management plan within prescribed timeframes per quarter by 31 December 2021 | 51% execution of identified risk management plan within prescribed timeframes per quarter by 31 December 2021 | none | none | Quartely Risk assessent reports | achived
KPA 2: INSTITUTIONAL DEVELOPMENT AND MUNICIPAL TRANSFORMATION
Strategic Objectives: To build capable, responsive, accountable, effective and efficient municipal institutions and administration
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence
[5 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience |  | Achieved / Not Achieved
municipal infrastructure grants (MIG) | number of MIG reports submitted to CoGHSTA | n/a |  | 12 | 6 MIG reports submitted to CoGHSTA by 31 December 2021 | 6 MIG reports submitted to CoGHSTA by 31 December 2021 | None | None | proof of submission | achieved
department of energy ( DOE) | number of INEP reports submitted to department of energy | n/a |  | 12 | INEP reports submitted to department of energy by 31 December 2021 | 5 INEP reports submitted to department of energy by 31 December 2021 | unable to retrieve proof of submission sent to DOE from the server | engaging with ICT unit for assistance | proof of submission | not achieved

## Infra projects
CAPITAL PROJECTS
KPA 4: BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Strategic objective: To provide for basic services delivery and sustainable infrastructural development
Ward No. | Project | key performance indicator | Original Budget R 000's 2021/22 | Expenditure | Audited Baseline 2019/20 | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience | Evidence | Achieved / Not Achieved
n/a | Air conditioners | % processing of procurement request submitted | 300000 | 0 | 50% | n/a | n/a | n/a | n/a | n/a | n/a
13 | Groblersdal landfill site | upgrading of groblersdal landfill site | 9050000 | 0.00 | new | appointment of service providers, site hand over and site establishment by 31 December 2021 | 54%-Project currently on hold | Project is currently on hold till further notice due to change of designs as per LEDET request | New drawings, as per new regulations done & sent to LEDET awaiting approval | tender advert | not achieved
13 | upgrading of Groblersdal traffic lights | number of traffic lights intersections upgraded in Groblersdal | 340000 | 0.00 | new | n/a | n/a | n/a | n/a | n/a | n/a
n/a | Supply and delivery of municipal vehicles | number of vehicles to be procured from the existing lease to buy contract | 800000 |  | new | 06 used vehicles to be procured by 31 December 2021 | 05 used vehicles to be procured by 31 December 2021 | None | None | no evidence | not achieved
24 | Reticulation of stands with electrical infrastructure at Ga Posa | number of stands reticulated with electrical infrastructure at Ga Posa | 2088000 | 289664.82 | 5% | construction of MV and LV by 31 December 2021 | contractor was introduced and handed over to the community in December 2021 | contractor was introduced and handed over to the community in December 2021 | Constultant to fast track the designs and submitt to the Municipality for approval | progress report | not achieved
12 | Reticulation of stands with electrical infrastructure at Maleoskop | designs of stands to be reticulated with electrical infrastructure | 3348000 | 0.00 | new | construction of MV and LV by 31 December 2021 | Project designs are done but awaiting presentation date from ESKOM in January 2022 | Delays in getting the information on the main line supplying the blue rich mine which the village is expected to connect on. | Constultant to fast track the designs and submitt to the Municipality for approval | progress report | not achieved
14 | Reticulation of stands with electrical infrastructure at Masakaneng | number of stands reticulated with electrical infrastructure at masakaneng | 5508000 | 0.00 | new | construction of MV and LV by 31 December 2021 | project still on design stage | Delays arosed from getting the consent letter from Masakaneng trust | Constultant to fast track the designs and submitt to the Municipality for approval | progress report | not achieved
14 | Reticulation of stands with electrical infrastructure at Matlala Lehwelere | number of stands reticulated with electrical infrastructure at Matlala Lehwelere | 3438000 | 358668 | new | construction of MV and LV by 31 December 2021 | contractor was introduced and handed over to the community in December 2021 | Late appointment of contractors | Contractor to resume work from the 10th January 2022 | progress report | not achieved
19 | Reticulation of stands with electrical infrastructure at Rondebosch | number of stands reticulated with electrical infrastructure at Rondebosch | 1206000 | 104, 458.74 | new | construction of MV and LV by 31 December 2021 | contractor was introduced and handed over to the community in December 2021 | Late appointment of contractors | Contractor to resume work from the 10th January 2022 | progress report | not achieved
23 | Reticulation of stands with electrical infrastructure at Vlakfontein | number of stands reticulated with electrical infrastructure at Vlakfontein | 5760000 | 118680.73 | new | construction of MV and LV by 31 December 2021 | contractor was introduced and handed over to the community in December 2021 | Late appointment of contractors | Contractor to resume work from the 10th January 2022 | progress report | not achieved
28 | Dipakapakeng access road | upgrading of 2.2km of Dipakapakeng road | 21750000 | 6447545.34 | new | 0km construction of the road by 31 December | Contractor busy with tipping base | none | None | progress report | achieved
27 | upgrading of Tafelkop stadium access road | ugrading of Tafelkop Stadium access road | 13184000 | 13075397.04 | new | appointment of service providers, site hand over and site establishment by 31 December 2021 | appointment of service providers, site hand over and site establishment by 31 December 2021 | none | None | appointment letter | achieved
11 | Bloompoort to Uitspanning access road | upgrading of Bloompoort to Uitspanning access road | 13000000 | 13026027.01 | new | appointment of service providers, site hand over and site establishment by 31 December 2021 | appointment of service providers, site hand over and site establishment by 31 December 2021 | none | None | appointment letter | achieved
31 | Motetema internal streets | construction of Motetema internal access streets | 1500000 | 0.00 | 11% | n/a | n/a | n/a | n/a | n/a | n/a
all wards | Rehabilitation of roads/ streets in various wards | Rehabilitation of 1.4km of roads/ streets in various wards | 2500000 | 0.00 | new | n/a | n/a | n/a | n/a | n/a | n/a
21 | upgrading of Kgaphamadi bus road stormwater control | designs of 5200m of Kgaphamadi bus road stormwater control | 1000000 | 0.00 | new | preliminary report completed by 31 December 2021 | no progress | Delays in preparing the design report for stormwater | Consultant to submitt the stormwater detailed designed to fast track the progress | preliminary report | not achieved
n/a | Culverts, road signs, stormwater channels | % expenditure on procurement of culverts road signs for stormwater channels | 500000 | 0.00 | new | 95% expenditure on procurement of culverts road signs for stormwater channels by 31 December 2021 | 0% expenditure on procurement of culverts road signs for stormwater channels by 31 December 2021 | project still on hold | None | expenditure report | not applicable

## Community Services
COMMUNITY SERVICES
KPA 4: BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Strategic Objectives: To provide for basic services delivery and sustainable infrastructural development
| Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[6 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience
| Waste management | number of reports for waste collection | n/a |  | 8% | 8 reports for waste collection by 31 December 2021 | 8 reports for waste collection by 31 December 2021 | None | None | waste collection reports | achieved
|  | number of waste received (tons) at landfill site | n/a |  | new | 200 tons of waste received at landfill site by 31 December 2021 | 2248 Tons of waste received at the Land ill site | None | None | reports on tons received | achieved
| Education/ Libraries | Number of initiatives held to promote library facilities | n/a |  | 3 | 2 initiatives held to promote library facilities by 31 December 2021 | 2 initiatives held to promote library facilities by 31 December 2021 | None | None | attendance register and reports | achieved
| Environmental management | number of enviromental awareness conducted | Opex |  | 3 | 2 enviromental awareness conducted by 31 December 2021 | 2 enviromental awareness conducted by 31 December 2021 | None | None | attendance register and reports | achieved
| Disaster management | Number of disaster awareness campaigns conducted | Opex |  | 3 | 2 disaster awareness campaigns conducted by 31 December 2021 | 2 disaster awareness campaigns conducted by 31 December 2021 | None | None | attendance register and reports | achieved
|  | % of disaster relief provided | Opex |  | new | 100% of disaster relief cases attended by 31 December 2021 | 100% of disaster relief cases attended | None | None | completed assessment form | achieved
|  | % of disaster cases reported and attended to within 48 hours | n/a |  | new | 100% of disaster cases reported and attended to within 48 hours by 31 December 2021 | 100% of disaster cases reported and attended to within 48 hours | None | None | completed assessment form | achieved
| safety and security | number of community safety forum meetings held | n/a |  | 3 | 2 community safety forum meetings held by 31 December 2021 | 2 community safety forum meetings held | None | None | reports and attendance register | achieved
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic objectives : To enhance good governance and public participation
| Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[6 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience
| Audit | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year | n/a |  | Qualified audit opinion | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year by 30 November 2021 | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year by 30 November 2021 | none | none | AGSA audit report | achieved
|  | % of Auditor General matters resolved as per the approved audit action plan by 30 June 2022 | n/a |  | 87% | n/a | n/a | n/a | n/a | n/a | n/a
|  | % Internal Audit Findings resolved per quarter as per the Audit Plan | n/a |  | 92% | 100% Internal Audit Findings resolved per quarter as per the Audit Plan by 31 December 2021 | 82% Internal Audit Findings resolved per quarter as per the Audit Plan by 31 December 2021 | None | Action plan implementation date not due | Quarterly IA follow up report | Not Achieved
| Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter | n/a |  | 100% | 50% execution of identified risk management plan within prescribed timeframes per quarter by 31 December 2021 | 58% execution of identified risk management plan within prescribed timeframes per quarter by 31 December 2021 | none | none | Quartely Risk assessent reports | achieved
CAPITAL PROJECTS
ward no | Project | key performance indicator | Original Budget R 000's 2021/22 | Expenditure | Audited Baseline 2019/20 | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience | Evidence | Achieved / Not Achieved
n/a | Disaster management centre emergency relief store room | Construction of Disaster management centre emergency relief store room | 100000 | 0 | new | placing of advertisement of service provider by 31 December 2021 | The project was halted to be Zero weighted during the Mid Term | Financial Constrains | Financial Constrains | copy of advertisement | not applicable
13 | upgrading and development of parks | number of parks to be developed and upgraded | 200000 | 0 | new | placing of advertisement of service provider by 31 December 2021 | The project was halted to be Zero weighted during the Mid Term | Financial Constrains | Financial Constrains | copy of advertisement | not applicable
13 | fencing of Elandsdoorn / Ntwane cemetery | fencing of Elandsdoorn / Ntwane cemetery | 500000 | 0 | 50% | placing of advertisement of service provider by 31 December 2021 | service provider appointed | None | None | copy of advertisement | Achieved
n/a | No illegal dumping boards | procurement of No illegal dumping boards | 200000 | 0 | new | placing of advertisement of service provider by 31 December 2021 | The project was halted to be Zero weighted during the Mid Term | Financial Constrains | Financial Constrains | copy of advertisement | not applicable
30 | Roosenekaal concrete palisade | upgrading of Roosenekaal concrete palisade | 100000 | 0 | new | placing of advertisement of service provider by 31 December 2021 | The project was halted to be Zero weighted during the Mid Term | Financial Constrains | Financial Constrains | copy of advertisement | not applicable
KPA 5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Objectives : To improve sound and municipal financial management
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience
SCM | Number of SCM deviation reports submitted to municipa manager (reduction of number of deviations) | n/a |  | 9 | Maximum of 1 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 31 December 2021 | 0 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 31 December 2021 | none | none | Signed deviation report | achieved

## Budget & Treasury
BUDGET AND TREASURY
KPA 4: BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Strategic Objectives: To provide basic services delivery and sustainable infrastructural development
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience
Indigents | number of households in municipal area registered as indigents | 207800 |  | 23% | 1176 households in municipal area registered as indigents by 31 December 2021 | 1713 households in municipal area registered as indigents by 31 December 2021 | none | none | indigent register | achieved
KPA 5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Objectives : To improve sound and sustainable municipal financial management
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience
Financial management | Cost coverage ratio (GKPI) | n/a |  | 0 | n/a | n/a | n/a | n/a | n/a | n/a
Revenue | % outstanding service debtors to revenue (GKPI) | n/a |  | 26% | n/a | n/a | n/a | n/a | n/a | n/a
Budget | Submission of MTRE Budget to Council 30 days before the start of the new financial year | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
Revenue | % of billed revenue collected | n/a |  | new | 40% of billed revenue collected by 31 December 2021 | 82% of billed revenue collected by 31 December 2021 | n/a | n/a | revenue report | achieved
AFS | Audited Annual Financial Statements (AFS) and Audit report submitted to council by 31 January 2022 | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
SCM | number of SCM deviation reports submitted to municipal manager (reduction of number of deviations ) | n/a |  | 9 | Maximum of 1 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 31 December 2021 | 0 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 31 December 2021 | n/a | n/a | Signed deviation report | achieved
Expenditure | % Payment of creditors within 30 days | n/a |  | 100% | 100% Payment of creditors within 30 days by 30 December 2021 | 100% Payment of creditors within 30 days by 30 December 2021 | n/a | n/a | creditors age analysis | achieved
Assets management | Number of assets verifications conducted | n/a |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic objectives : To enhance good governance and public participation
Programme | KPI | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 2nd Qtr target | Progress to date | Challenges | Reason for Varience
Audit | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year | n/a |  | Qualified audit opinion | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year by 30 November 2021 | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year by 30 November 2021 | none | none | AGSA audit report | Achieved
| % Auditor General matters resolved as per the approved audit action plan |  |  | 87% | n/a | n/a | n/a | n/a | n/a | n/a
| % Internal Audit Findings resolved per quarter as per the Audit Plan | n/a |  | 92% | 100% Internal Audit Findings resolved per quarter as per the Audit Plan by 31 December 2021 | 100% Internal Audit Findings resolved per quarter as per the Audit Plan by 31 December 2021 | None | Action plan implementation date not due | Quarterly IA follow up report | not achieved
Risk Management | % execution of identified risk management plan within prescribed timeframes per quarter | n/a |  | 100% | 50% execution of identified risk management plan within prescribed timeframes per quarter by 31 December 2021 | 51% execution of identified risk management plan within prescribed timeframes per quarter by 31 December 2021 | none | none | Quartely Risk assessent reports | achieved
CAPITAL PROJECTS
ward no | Project | key performance indicator | Original Budget R 000's 2021/22 | Expenditure | Audited Baseline 2019/20 | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience | Evidence | Achieved / Not Achieved
n/a | forklift | % procurement of forklift | 100000 |  | new | n/a | n/a | n/a | n/a | n/a | n/a

## Executive support
EXECUTIVE SUPPORT
KPA 4: BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Strategic Objectives: To provide basic services delivery and sustainable infrastructural development
Programme | Key performance indicator | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience
Transversal programmes | number of Transversal programmes implemented in terms of mainstreaming with respect to HIV/AIDS, Gender, Disabled, Woman and Children Rights, eldery and moral re-generation | Opex |  | 4 | n/a | n/a | n/a | n/a | n/a | n/a
KPA 6: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic objectives : To enhance good governance and public participation
Programme | Key performance indicator | Budget Source | Expenditure | Audited Baseline 2019/20 | 2021/22 |  |  |  | Evidence | Achieved / Not Achieved
[5 empty] | 2nd Qtr Target | Progress to date | Challenges | Reason for Varience
MPAC | number of MPAC quartely reports submitted to council | n/a |  | 3 | 2 MPAC quartely reports submitted to council by 31 December 2021 | 0 MPAC quartely reports submitted to council by 31 December 2021 | newly appointed MPAC councillors members were not yet approved by council, hence they where no Mpac activities | To be submitted to councill after the offical handover from the previous Mpac committee | council resolution | not achieved
| number of MPAC outreaches initiated | 1000000 |  | 3 | n/a | n/a | n/a | n/a | n/a | n/a
Mayoral campaigns (event promotions) | number of Mayoral outreach projects initiated | 623400 |  | 2 | n/a | n/a | n/a | n/a | n/a | n/a
Speakers programme (event promotions) | number of Speaker's outreach projects initiated | 207800 |  | 2 | n/a | n/a | n/a | n/a | n/a | n/a
Ward committee | number of ward committeee reports submitted to council quartely | n/a |  | 2 | n/a | n/a | n/a | n/a | n/a | n/a
youth programmes | number of youth programmes initiated | Opex |  | 1 | n/a | n/a | n/a | n/a | n/a | n/a
communications | number of municipal newsletter printed/ produced | opex |  | 10000 | 2500 municipal newsletter printed/ produced by 31 December 2021 | 4000 municipal newsletter printed/ produced by 31 December 2021 | none | none | delivery note and copy of the newsletter | Achieved
| reviewal of communication strategy | n/a |  | 0% | n/a | n/a | n/a | n/a | n/a | n/a
customer services | % of community complaints received and processed | n/a |  | 100% | 100% of community complaints received and processed by 31 December 2021 | 1=100% of community complaints received and processed by 31 December 2021 | none | none | community complaints register | achieved
customer care | number of customer care implementaion plan and monitoring conducted | n/a |  | new | 2 customer care implementaion plan and monitoring conducted by 31 December 2021 | 2 customer care implementaion plan and monitoring conducted by 31 December 2021 | the plan was not monitored | to ensure monitoring of report in future | implementation and monitoring register | achieved
council resolutions | % council resolutions implemented | n/a |  | new | 50% council resolutions implemented by 31 December 2021 | 5/6x100=83% council resolutions implemented by 31 December 2021 | none | none | resolution register | achieved
SCM | number of SCM deviation reports submitted to municipal manager (reduction of number of deviations ) | n/a |  | 9 | Maximum of 1 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 31 December 2021 | 0 SCM deviation reports submitted to municipal manager (reduction of number of deviations) by 31 December 2021 | none | none | Signed deviation report | achieved
Audit | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year | n/a |  | Qualified audit opinion | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year by 30 November 2021 | Obtain an Unqualified Auditor General opinion for the 2020/2021 financial year by 30 November 2021 | none | none | AGSA audit report | achieved
| % Auditor General matters resolved as per the approved audit action plan |  |  | 87% | n/a | n/a | n/a | n/a | n/a | n/a
Audit | % Internal Audit Findings resolved per quarter as per the Audit Plan | n/a |  | 92% | 100% Internal Audit Findings resolved per quarter as per the Audit Plan by 31 December 2021 | 80% Internal Audit Findings resolved per quarter as per the Audit Plan by 31 December 2021 | None | The capacity building programme in process of development | Quarterly IA follow up report | Not Achieved
Risk management | % execution of identified risk management plan within prescribed timeframes per quarter | n/a |  | 100% | 50% execution of identified risk management plan within prescribed timeframes per quarter by 31 December 2021 | 70% execution of identified risk management plan within prescribed timeframes per quarter by 31 December 2021 | none | none | Quartely Risk assessent reports | achieved
M.M KGWALE | [7 empty] | DATE
MUNICIPAL MANAGER